Acquisition Management System Guidance

Earned Value Management Guide

March 2012

Earned Value Management Guidance

Cover Page  
SECTION I: FAA EARNED VALUE MANAGEMENT PROGRAM    
Introduction    
Program Description    
Roles and Responsibilities    
SECTION 2: EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA PROGRAMS    
Earned Value Management for FAA Programs  
Basic Features of Earned Value Management  
Process for Implementing EVMS    
ANSI/EIA-748 Standard Guidelines for EVMS    
Tailoring the EVMS    
SECTION 3: EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA CONTRACTS    
Earned Value Management for FAA Contracts  Tailoring the EVMS    
Pre-Contract Award Activities  
Post Contract Award Activities  
SECTION 4: FAA EARNED VALUE MANAGEMENT SYSTEMS ACCEPTANCE APPROACH    
EVMS Acceptance Approach and Scope    
FAA Programs EVMS Acceptance Process  
FAA Contractors EVMS Acceptance Process    
Earned Value Management System Surveillance    
APPENDIX 1 -- EARNED VALUE MANAGEMENT REFERENCES

SECTION I: FAA EARNED VALUE MANAGEMENT PROGRAM

Introduction

The effective application of Earned Value Management (EVM) in support of integrated program management provides both the FAA and its contractors with timely, accurate, and integrated cost, schedule and technical performance information, for both the total capital investment program and individual supporting contracts.  EVM continuously measures the quantity and value of work completed and enables the forecasting of reliable estimates of future performance.  The approach has proven to be an effective management tool for programs with performance risk or high interest to management.

The three aspects of earned value referenced in this Guide are defined as follows:

- Earned Value Management (EVM) is a methodology that integrates a program’s (or contract’s) work scope, schedule, and resources with risk management, thereby providing government and contractor managers with objective visibility into progress on their programs and the ability to manage effectively. By reliably identifying trends and problems early, EVM helps program managers effectively plan, control, and manage programs so they can take corrective action and re-plan the work, if necessary.  Systematic implementation of EVM throughout the organization facilitates comparison of program performance, enabling managers to make better-informed decisions.

- Earned Value Management System (EVMS) is the integrated set of processes, applications and practice that follow the guidelines in American National Standard ANSI/EIA-748, “Earned Value Management Systems.”  The ANSI/EIA-748 guidelines describe the attributes of an effectively integrated cost, schedule, and technical performance management system.

- Earned Value (EV) is the amount or volume of work completed to date, also referred to as the budgeted cost for work actually accomplished or performed.  When compared to the planned value for the work and its actual cost, earned value provides objective measures of schedule and cost performance.

The FAA EVM Guide provides specific implementation guidance to program managers and contracting officers in support of the policy established in the Acquisition Management System (AMS) for EVM systems use on FAA programs and contracts.  Additionally, the Guide provides FAA program managers, contracting officers, executives, executive committees, and review boards with a further understanding of the application of EVM concepts in support of program management practices in FAA that will contribute to improved program performance.

Program Description

The FAA’s EVM program provides for the effective and consistent implementation of earned value program management across FAA’s capital investment portfolio, including programs supporting the National Airspace System (NAS), agency-wide information technology programs, and other major investment programs such as safety-related programs.  The following key components of the EVM program are addressed in this Guide:

- EVM Implementation on FAA Programs;

- EVM Implementation on FAA Contracts; and

- EVM Acceptance and Surveillance Processes

Section 2.0 provides guidance on which programs are required by policy to use EVM, describes its basic features, and discusses implementation on FAA investment programs.  Section 3.0 provides guidance on which contracts are required by policy to use EVM and discusses how it is implemented contractually, pre-award and post-award activities that support the process of placing EVM on a contract.

Additionally, the EVM program includes support processes for program managers in the areas of EVM training, Exhibit 300 preparation, and EVMS program assessments and transition plans that will be addressed in future releases of this Guide.

Reporting EVM Performance Data to Department of Transportation (DOT).   For FAA major systems or capital investments, the Office of Management and Budget (OMB) tracks and ultimately approves baseline changes through the budgeting process and the President’s Management Agenda “green” level of performance.   OMB requires the FAA to report major capital investment program performance variances for cost and schedule.  Program managers must submit monthly and cumulative EVM data and variance analyses (and corrective action plans if necessary) through the FAA Chief Information Officer (AIO) to the Department of Transportation Chief Information Officer (S-80).  DOT submits data to OMB quarterly.

EVM Applications.  The FAA’s EVM program uses applications to analyze and report EVM performance data (EVM analysis tools).  Program managers may likewise use this type of EVM application to analyze and report program performance, as well as applications used to manage programs and produce EVM data (EVM “engines”).  A number of commercially available applications produce, receive, analyze, and report data and should be used by program managers to efficiently manage EVM data.  FAA has not yet selected either a standard EVM engine or a standard analysis tool, but may do so in the future.  Program offices should contact the EVM Focal Point to discuss their options.

Roles and Responsibilities

The Acquisition Executive and the Chief Information Officer are jointly responsible for the FAA EVM program and its consistent application across the capital investment portfolio, including the individual supporting contracts.  Correspondingly, the primary roles and responsibilities for the EVM program are assigned to the Acquisition and Business Services (ACQ), and the Office of the Chief Information Officer (AIO)  However, the program manager and contracting officer have the most critical roles and will be described first.

To meet the EVM responsibilities listed in policy, the program manager:

- Prepares the investment program for an EVMS validation review, if required, in accordance with AMS Section 4.16, EVM;

- Ensures the program management team is adequately trained in program management and earned value management techniques;

- Incorporates contract performance reports into the program performance information consistently using the Program Work Breakdown Structure;

- Conducts contractor EVMS surveillance when EVMS compliance or EVMS acceptance is required;

- Develops the EVM Surveillance Plan

- Ensures timely preparation and update of the OMB Exhibit 300 annually; and

- Estimates cost and schedule at completion based on performance to date, and when required, initiates a request for re-baselining in accordance with FAA policy.

To meet the EVM responsibilities listed in policy, the contracting officer:

- Advises the team preparing the Screening Information Request on the proper use of contract clauses and supporting documentation for EVM;

- Formally receives, delivers comments, and accepts EVM-related deliverables; and

- Coordinates with the FAA EVM Focal Point to ensure that contractor EVM systems are validated and formally accepted when required;

- Issues and conveys the FAA EVMS Letter of Acceptance and Advance Agreement, as applicable, and

- Coordinates with program manager and the EVM Focal Point to ensure EVMS surveillance is conducted consistent with the contract EVM requirement

The EVM Focal Point and AIO work closely together to ensure the EVM program is applied consistently across the FAA.

To meet EVM responsibilities listed in policy, the EVM Focal Point:

- Develops policy and guidance for EVM in support of the AMS;

- Consults with teams on EVM issues during source selection;

- Advises and assists programs with Integrated Baseline Reviews;

- Coordinates and conducts EVMS reviews (initial validation reviews, post-acceptance reviews and reviews for cause) and reviews contractor EVMS plans to verify initial and continuing compliance of contractor EVM systems with the guidelines of the EVMS Standard (ANSI/EIA-748);

- Recommend contractor EVMS acceptance to the FAA Acquisition Executive and Contracting Officer based on the results and closure of EVMS reviews;

- Maintains a list of contractor EVM systems accepted by the FAA and coordinate with other Government Agencies regarding acceptance of contractor EVM systems;

- Develops AMS guidance and provides oversight for contractor EVMS surveillance;

- Reviews and approves the Surveillance Plans

- Manages the EVM training program and curriculum; and

- Serves as a subject-matter expert when reviewing and commenting on the Exhibit 300, Cost and Schedule Performance (Part 2, Section C) during the annual preparation process for investment programs.

To meet the EVM responsibilities listed in policy, the AIO (Value Management Office):

- Coordinates and manages the preparation of agency Exhibit 300s, which describes the programs’ Performance Based Management System (EVMS), the program baseline, schedule and cost performance, variance analysis, and corrective action plans, when required;

- Develops AMS guidance and conducts program performance surveillance, including the Program EVMS; and

- Assists in the development of EVM policy and guidance in support of the AMS as it develops and/or changes.

To meet the EVM responsibilities listed in policy, Financial Services (ABA):

- Performs the AMS EVMS surveillance in collaboration with AIO, as part of program-level performance surveillance.

- The Service Units and Line of Business organizations, jointly with ABA and AIO, will ensure each affected Service Unit and Line of Business organization is fully engaged and compliant with all phases of planning, performing and reporting steps of the surveillance process given in the EVM Guide as incorporated into the AMS.

SECTION 2: EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA PROGRAMS

Earned Value Management for FAA Programs

The OMB and AMS policies require development / modernization / enhancement programs to use EVM based on the guidelines in the American National Standard ANSI/EIA-748.  FAA programs apply EVM methodologies to the total program effort, including both government and contractor work, to better manage complex, high-risk, high-cost, or high-visibility efforts.  While development / modernization / enhancement programs primarily occur during solution implementation, the work, as approved, may start during final investment analysis and may continue during in-service management.

FAA programs may utilize multiple sources to accomplish the work of the program and commonly assign work to the following performing organizations that must be included in the EVMS:

Government Organizations.  Government organizations and personnel (Full-Time Equivalents – FTEs), while commonly used to perform program management and oversight, may also perform engineering, testing, deployment, and logistics support functions.  All work and program activities performed by government personnel are assigned using the program baseline work breakdown structure (WBS) and are managed using EVM.  FAA programs required to use EVM must include resources for all government Development Modernization and Enhancement effort included in the IDA-approved program baseline.

Major Contractors.  Major contractors commonly are employed in the areas of design, engineering, development, deployment, and support functions.  All work and program activities performed by major contractors are assigned using the program baseline WBS and are managed using EVM.  FAA programs required to use EVM must include resources for all major contractor effort included in the IDA approved program baseline.  Implementation of EVM on major contractor effort must be consistent with AMS Earned Value Management policy, paragraph 4.16.2 Contract Requirements. (See Section 3.0)

Support Contractors.  Support contractors commonly perform support roles in one or more areas of program management, engineering, configuration management, test, and logistics.  All work and program activities performed by support contractors are assigned using the program baseline WBS and are managed using EVM.  FAA programs required to use EVM must include resources for all support contractor effort included in the -approved program baseline.  Implementation of EVM on support contractor effort must be consistent with AMS Earned Value Management policy, paragraph 4.16.2 Contract Requirements. (See Section 3.0)

Investment programs organize work using the FAA standard lifecycle WBS that follows the AMS lifecycle.  The use of EVMS during the planning phases (WBS 1.0 and 2.0) is considered a best practice when the work involves prototyping or testing.  EVMS is required by AMS policy when the FAA approving authority at the final investment decision approves the program baseline and when a program commences development work prior to the final investment decision.  EVM is used during the solution development phase (WBS 3.0), solution implementation phase (WBS 4.0), and in service management phase activities (WBS 5.0), commonly funded by Facilities and Equipment (F&E) funds, including the NAS “Hand-Off” activities, in order to promote the integrity of the performance measurement baseline.  The primary consideration in deciding to use EVM is the nature of the work.  The decision should not be arbitrarily based on program phase or funding source.

Operational and steady-state programs or useful segments funded by Operations and Maintenance (O&M) funds are not required to use EVM, but may do so when the nature of the work lends itself to earned value performance measurement.  These programs perform an annual operational analysis to confirm that realized benefits outweigh costs and that they continue to support agency goals and user needs.

Basic Features of Earned Value Management

EVM methodology periodically (normally monthly, but more frequently when necessary) measures achievement objectively against established goals in a performance baseline plan, helping projects stay on course.  It assists in the identification of potential cost and schedule problems early, before they become unmanageable or unrecoverable, and enables estimates of final program cost and schedule.  Appendix 1, EVM References, provides multiple sources for the definition and formulas of standard EVM performance measures.

EVM requires the fundamental program management principles of planning, organizing, measuring, and controlling to be implemented systematically to produce a product or service.  To apply EVM effectively, program managers:

- Plan all work to completion;

- Establish a program baseline work breakdown structure consistent with the program phase or segment(s) approved for execution and funding, as defined in the Implementation Strategy and Planning Document (ISPD);

- Break down the work into manageable capital asset / product components and assign them to a responsible organization;

- Integrate cost, schedule, and performance objectives into a baseline plan against which progress is measured;

- Record actual costs;

- Objectively measure performance against the baseline plan;

- Analyze variances, forecast impacts, and base estimates at completion on actual performance to date;

- Control and document changes to the performance measurement baseline; and

- Use earned value information in the organization’s management processes.

Process for Implementing EVMS

The generic steps for establishing an EVMS are outlined below.  In addition, FAA’s EVM Training Program and Appendix 1, EVM References provide more detailed descriptions of implementation.

- Establish a management control system that meets the guidelines in ANSI/EIA-748;

- Create an integrated performance measurement baseline (resource-loaded schedule of work to be performed at the lowest level required for performance measurement);

- Establish a work authorization system that assigns responsibility for and controls changes to the performance measurement baseline;

- Earn value for planned budgets as work is completed;

- Provide status against the baseline plan and identify significant schedule and cost variances;

- Analyze variances for early warning signs and take corrective action as necessary; and

- Estimate final cost and schedule outcomes

ANSI/EIA-748 Standard Guidelines for EVMS

ANSI/EIA-748 contains guidelines for establishing and applying an integrated management system for cost, schedule, and technical performance.  The Standard contains 32 guidelines, grouped into five major categories:

- Organization;

- Planning, Scheduling, and Budgeting;

- Accounting Considerations;

- Analysis and Management Reports; and

- Revisions and Data Maintenance

Due to variations in organizations, products, and working relationships, it is impossible to prescribe a universal system for cost and schedule control.  Therefore, the guidelines in ANSI/EIA-748 do not describe a system.  Instead, they state the qualities and operational considerations of an integrated management system without mandating detailed system characteristics.  In designing and implementing an EVMS, the primary objective of the FAA or contractor should be effective management and control.  FAA and contractor organizations have flexibility under this guideline approach to develop an EVMS most suited to their management needs.

The guidelines do not address all FAA needs for day-to-day or week-to-week internal control, such as status reports, reviews, and communications.  These internal controls are characteristics of good management and should be used with EVM to provide insight and information necessary to make informed decisions.  The FAA Program Control EVM Assessment Review Criteria reflects the NDIA Intent Guide for Earned Value Management Systems using FAA terms, processes, procedures and documents.  It also provides additional insight into the 32 guidelines and describes the typical attributes and objective evidence that support compliance with a given guideline.

Tailoring the EVMS

The program manager, assisted by functional experts such as systems engineers, cost performance specialists, and financial analysts, assesses the program’s anticipated size, complexity, risk, criticality, type of contract, and other factors to select the performance management methodology and reporting best suited for effective management control.  The program manager, considering all risk factors, tailors EVMS requirements to the program.  For example, full compliance with the ANSI/EIA-748 guidelines, with no tailoring, would provide necessary insight into progress on a high-risk program involving a critical, complex integration effort.

Alternatively, appropriate tailoring of EVMS requirements could provide sufficient visibility into performance for a lower-risk program.  Once the program manager characterizes the overall nature of the program, EVMS requirements are tailored to ensure an appropriate level of performance measurement and control.  Examples of ways an EVMS may be tailored include:

| Nature of Program | ANSI/EIA Guidelines | Performance Reports | EVMS Validation | Performance Measurement Baseline | Earning Performance |
| --- | --- | --- | --- | --- | --- |
| Lower Risk (E.g., off the shelf, low- risk schedule, fixed-price contract) | Core principles | Other reports – streamlined | None | Self assessed | Logical means at higher level |
|  | Tailored compliance | Contract Performance Report - tailored (delete formats) | TBD | Integrated Baseline Review | Control account level |
| Higher Risk (E.g., complex integration; Leading-edge technology, risk-sharing contract) | Full compliance | Contract Performance Report (all formats) | Government involved | Integrated Baseline Review | Control account level |

- At the program level, EVM is required for contracts with one base year plus multiple option years.  Also EVM is required for five year incrementally funded programs.  However, EVM is not required for programs or projects lasting less than one year, but may be used when an existing EVMS can provide reliable information soon after initiation and the program manager has ready access to the information.  Although EVM may not be required, it is important that appropriate scheduling, risk, and requirements management practices be applied for effective monitoring and control.

SECTION 3: EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA CONTRACTS

Earned Value Management for FAA Contracts

Investment programs or capital investments determined to be “major programs” with an Exhibit 300 reporting requirement to OMB, are required by AMS policy to use an EVMS to manage all development / modernization / enhancement work, including the work assigned to all contractors, http://fast.faa.gov/ .  This applies to all contract types and contract sizes.  The implementation approach is consistent with the acquisition strategy of the program as documented in the Implementation Strategy and Planning Document, section 3.2, Program Control. EVMS for contractor effort must be implemented consistent with AMS Earned Value Management policy, paragraph 4.16.2 Contract Requirements.  When EVM reporting is obtained from a contractor, the contractual required reports include the Contract Performance Report (CPR). These reports may be tailored and customized in accordance with their respective Data Item Descriptions (DID), specific program risks, and performance measurement metrics/reports included in the Implementation Strategy and Planning Document.

Integrated Master Schedule (IMS) reports will be obtained consistent with AMS Earned Value Management policy, paragraph 4.16.2 Contract Requirement.  These reports may be tailored and customized in accordance with their respective Data Item Descriptions (DID), the specific program risks, and performance measurement metrics/reports included in the Implementation Strategy and Planning document.

Investment programs not designated as “major systems” and as a result having no Exhibit 300 reporting requirement to OMB and solely responsible to the designated Investment Decision Authority (IDA) also follow the policy in AMS in determining the application of EVMS and associated reporting of development / modernization / enhancement work assigned to contractors.

Major Contracts and Subcontracts.  When a program awards a contract greater than $10M for development / modernization / enhancement work, the contract effort is managed by an EVMS.  A CPR and IMS are obtained consistent with the Implementation Strategy and Planning Document, section 3.2, Program Control. These reports may be tailored and customized in accordance with their respective Data Item Descriptions (DID), specific program risks, and performance measurement metrics/reports included in the Implementation Strategy and Planning Document.  The CPR and IMS DID’s may be found in the AMS FAST under the Procurement Tool Box.  Contractor IBRs are performed to ensure planning is adequate.  The contractually required EVMS used by each contractor must meet the guidelines in American National Standard ANSI/EIA-748 and be certified in accordance with the process outlined in Section 4.

Small Contracts and Subcontracts.  When a program awards a contract less than $10M for development / modernization / enhancement work, the contract may be managed using an EVMS following the optional policy guidelines outlined in AMS.  A CPR and IMS are optional requirements on the contract.  These reports may be tailored in accordance with their respective DIDs and the specific risks and requirements of the contract.  IBRs may be performed to ensure planning is adequate.  The EVMS, if required, should follow the guidelines of American National Standard ANSI/EIA-748, and an acceptance of the EVMS may be required in accordance with Section 4.

Tailoring the EVMS

The selection of contract type is a decision made independent of EVM considerations.  The decision should be based on the nature of the work and anticipated risk.  Any contract that provides for risk sharing (cost type or fixed-price incentive) should include appropriate EVM application and reporting requirements.  Decisions on contract type should not be made to avoid placing EVM on the contract; conversely, EVM should not be applied when it is not appropriate; for example, when buying commercial items based on competitively determined market prices.

Pre-Contract Award Activities

Performance Reports.  The program manager uses contractor performance information derived from the EVMS along with other management information, including technical and schedule-related deliverables to inform the decision-making process throughout the program lifecycle.  Establishing the basis for program metrics and reporting prior to contract award are critical success factors.  Based on a realistic assessment of what can and will be needed, the program manager determines which contract type is best suited based on anticipated risk and what performance reporting, appropriately tailored, is required.  The screening information request and resulting contract are written to reflect the type of report and reporting level needed for effective program control.  Performance reporting options, tailored as needed, are:

- Contract Performance Report (CPR) – Full Reporting.  This is used for high-risk, complex, large programs, when the government shares significant risk or when management interest requires assurance that contractor and subcontractor’s cost and schedule management control systems are adequate.  All five formats of the CPR should be required, with specific reporting levels identified;

- Contract Performance Report - Tailored.  This is intended for less complex programs with lower risk where the contractor assumes a greater share of the risk.  Formats 2 and 4 of the CPR are often not required and the reporting level may be higher in the contract WBS; and

- Other authorized reports - any other performance reports that the program manager believes appropriate and necessary.

Data Item Descriptions.  Performance reports contain the data the program manager needs to manage the contract consistent with contract requirements for the CPR.  When a CPR is required, the DI-MGMT- 81466 DID is included in the screening information request as a guide for obtaining the CPR and tailoring report requirements to appropriate information.  DIDs are available on-line in the Statement of Work Generator in FAST or from the DoD EVM website under EVM Policy and Guidance.

Contract Clauses.  For contracts requiring full compliance with the EVMS Standard and the submission of a CPR, the screening information request includes both AMS provision 1.13-1, “Notice of Earned Value Management System Requirements” and contract clause 1.13-2, “Earned Value Management Systems.”

Contract Work Breakdown Structure.  A preliminary contract work breakdown structure (CWBS) is prepared by the program manager and included in the screening information request.  The program manager ensures the CWBS is consistent and compatible with the program baseline WBS to facilitate incorporation of contractor performance information into program performance reports.  The CWBS should not specify an excessive number of lower-level elements because it may impinge on the contractor’s normal method of operations or result in excessive reporting requirements.  When determining the level for reporting, the program manager should extend the CWBS only to the level that allows visibility into those high-cost, high-risk, or specific areas critical to the success of the program.  The statement of work (SOW) requires the contractor to extend the CWBS to meaningful management or product-oriented lower levels that reflect the way it does business, and to prepare and deliver a CWBS Index and Dictionary.  The contractor should have complete flexibility in extending the CWBS to capture all high-cost and high-risk elements.  The reporting of progress, performance, and engineering evaluations, as well as financial data and variance analysis, are based on the CWBS.  However, any extension proposed by the contractor needs to be traceable directly to the CWBS prepared by the program manager, unless an alternative has been agreed to.

Network Schedule. To ensure the management control system is integrated, the program manager defines requirements in the SOW for a network logic schedule showing the sequence of events and critical path for program milestones or deliverables.  By managing the critical paths (the path in the schedule with zero slack time or float) will contribute to timely and successful completion of programs.

Statement of Work (SOW). The contract SOW reflects the requirement for an EVMS.  The SOW should require the contractor to use appropriately tailored-earned value information as a basis for preparing the CPR and to integrate and present cost, schedule, and technical performance information with risk-management reporting at regularly scheduled program status reviews.  Specific SIR and contract clauses are available as part of the FAST procurement guidance.  Examples of SOW language for EVMS, CWBS, and network schedule are as follows; these examples or the more detailed standard FAA clauses should be modified to fit particular program requirements.

Earned Value Management System (EVMS)

The Contractor must utilize an EVMS for planning, controlling, and integrating project scope, schedule, and resources.  The Contractor must provide documentation that their EVMS has been accepted by a Government Agency.  If the Contractor proposes to use an EVMS or similar system that has not been formally accepted, the Contractor must submit a comprehensive plan to develop, implement and validate an EVMS that complies with the EVMS Standard (ANSI/EIA-748).

Contract Work Breakdown Structure (CWBS)

The Contractor must extend the CWBS specified in the contract to a level sufficient to identify all high-cost or high-risk elements and any elements of special interest to management.  The CWBS must be extended to the necessary level of detail to support development of a logical and efficient sequence of tasks designed to accomplish the effort described in the Contract.

Network Logic Schedule (NLS)

The Contractor must establish a NLS that describes the sequence of events needed to accomplish the requirements of this contract and that reflects CWBS elements.  The Contractor must ensure the NLS portrays an integrated schedule plan to meet the milestones and delivery requirements of this contract.  The NLS must identify the program’s critical path.  The NLS is to be constructed using a software tool compatible with standard scheduling software.  The Contractor must submit the NLS at the post-award conference and an updated version monthly in program status reviews.

Proposal Evaluation.

As part of proposal submission, offerors provide information describing their system for planning, controlling, integrating, and reporting performance.  Their proposed EVMS is subject to validation and formal acceptance by the FAA to ensure compliance of the proposed EVMS with the EVMS Standard (ANSI/EIA-748).

- Offerors may provide evidence that the proposed EVMS has been independently validated and formally accepted. This evidence should include 1) identification of the organization that granted the formal acceptance and 2) evidence of EVMS surveillance that the contractor’s EVMS remains compliant with the EVMS Standard (ANSI/EIA-748).

- If the EVMS has not been validated and formally accepted, offerors provide an EVM Implementation Plan for doing so.

In some situations it may be beneficial to the proposal evaluation process to conduct an Integrated Baseline Review (IBR) for each offeror before contract award if time and resources permit.  Guidance on the IBR process is provided in the FAA Program Level IBR Guide.

Contract Award.  The awarded contract includes SOW tasks instructing the contractor to provide integrated earned value-based cost and schedule reporting.  It also requires the contractor to extend the negotiated CWBS and use it as a basis for planning, budgeting, and reporting.  The applicable CPR clause and corresponding DID are also included in the contract.  If applicable, there may also be contractual agreements on subcontractor performance reporting.  EVM-related activities and outputs ending at contract award are summarized below:

| Activity | Output |
| --- | --- |
| Determine management system and reporting requirements | Reporting: - CPR - full guidelines, all formats - CPR - tailored - Other performance reports |
| Prepare Screening Information Request (SIR) | SIR includes: - CDRL/DID - CPR, or other report - SOW language - CWBS - EVMS Clauses |
| Evaluate offeror proposals | Evaluation addresses: - Contractor’s description of its EVMS - Potential pre-award IBR - Proposed CWBS changes - EVMS Implementation Plan |
| Negotiate contract and select offeror | Negotiation finalizes: - CDRL/DID tailoring - Proposed CWBS changes, if any - Contractor EVMS management procedures |
| Award contract | Final contract includes: - CDRL/DID - SOW language - CWBS - EVMS Clauses |

Post Contract Award Activities

If not conducted prior to contract award, the program manager conducts a comprehensive IBR of the program baseline for major contracts within 90 to 180 days of contract award or program baseline establishment.  An IBR conducted after award uses earned-value plans and data reported by the contractor, ensures the data are analyzed and coordinated among program personnel, and if applicable ensures follow-up surveillance of the contractor’s EVMS.

Integrated Baseline Review.  An IBR evaluates program management’s and contractor’s implementation of the performance measurement baseline.  An IBR is intended to ensure the government and contractor mutually understand program scope, schedule, resources, inherent risk, and management approach, and to ensure early and adequate planning.  The IBR identifies risk items that naturally become part of the risk management plan.  The IBR is a continuous part of the government and contractor program management process.  An updated IBR is also conducted after award of significant contract options or contract modifications.  Guidance on the IBR process is provided in the Program Level IBR Guide.

Analyze Data.  Functional specialists on the program, such as software or systems engineers, are designated as control account managers, with responsibility for reviewing reported cost, schedule, and technical progress related to their functional area.  Cross-fertilization of this information improves program decision-making by integrating cost, schedule, and technical considerations, and assures the program of the consistency of reported information from various sources.  The contractor delivers the first CPR or other performance report shortly after contract award.  The program manager and functional specialists immediately review the data.  Thresholds are established for detailed analysis of cost and schedule variances.  The analysis examines the causes for variances, identifies corrective actions, and assesses impact on the overall program.  Cost and schedule variances are charted and compared against other data that may be available such as progress reports, technical interchange meeting minutes, etc.  It is also important for cost and schedule status information reported in performance reports to be discussed along with technical status at regularly scheduled meetings and program reviews with the contractor.

Address Variances.  The Performance Measurement Baseline (PMB) is the agreed to plan for executing the program.  Variances from the plan are expected to occur because the PMB and actual execution normally differ.  Variance analysis provides information on:

- Cause and effect - How and why did the variance happen?

- Consequence - What is the effect of the variance on this work package, control account, and program baseline WBS element and on other work packages, controls accounts and program baseline WBS elements?

- Correction - Is it possible to recover?  What is the recovery plan?  Do other tasks require management attention to mitigate the effect of the variance?  If it is not possible to recover and get back on plan, what must be done to replan the effort?

Analysis of variances begins at the control account level and continues upward through the WBS and program team until all effects are accounted for and mitigated.  Detailed analysis should be performed for all significant variances.

Links to Risk Management.  Throughout execution of the contract, the program manager ensures the results of EVM analysis and metrics are linked to the risk management plan.  Risk mitigation plans are included in the EVM plan to track and manage risk mitigation actions.

SECTION 4: FAA EARNED VALUE MANAGEMENT SYSTEMS ACCEPTANCE APPROACH

EVM Systems Acceptance Approach and Scope

FAA programs required by policy, http://fast.faa.gov/, to use an EVMS and required to demonstrate that the EVMS meets the guidelines of EVMS Standard (ANSI/EIA-748) are assessed and formally accepted by the Chief Information Officer. (AIO).   Additionally, AIO is responsible for program performance surveillance, which includes EVMS surveillance to ensure the program continues to meet the guidelines of the EVMS Standard (ANSI/EIA-748).

FAA contractors required by contract to use an EVMS and to demonstrate formal acceptance of the EVMS as meeting the guidelines of the EVMS Standard (ANSI/EIA-748) undergo an EVMS Validation Review conducted by he contracting officer and the EVM Focal Point.  The EVM Focal Point is responsible for performing contractor EVMS validation reviews and oversees contractor EVMS surveillance.  The EVM Focal Point determines whether a contractor requires an EVMS validation review or if an existing acceptance by a Government Agency and current EVM surveillance process are acceptable.  The FAA EVM Focal Point establishes agreements with other government agencies to recognize contractor EVMS acceptances and surveillance reports.

FAA Programs EVM Systems Acceptance Process

AIO with the support of the EVM Focal Point conducts EVMS validation Reviews on programs prior to the final investment decision or as requested.  The assessment includes a review of program documentation and interviews with program management and key personnel.  The assessment includes a review of procedures and practices on the use of earned value data by the program team.  The review focuses on three main areas concerning use of earned value data:

- Program planning of schedule and cost; including their integration and baseline control with the technical scope as defined in the program baseline WBS;

- Program performance data analysis and reporting; including the usefulness and effectiveness to the program team to manage schedule and cost; and the

- Availability of timely program performance data used by the program team to anticipate and mitigate program risks.

The program EVM review includes data for government effort, major contractors, and support contractors.

Program management EVM processes are assessed to determine if they meet the intent of EVMS Standard (ANSI/EIA-748).  The bases for the assessment are the EVMS Standard (ANSI/EIA-748) guidelines and the FAA Program Control EVM Assessment Review Criteria.  The assessment uses a Red/Yellow/Green rating system to assess EVM implementation for each guideline.  The scale for determining EVM compliance for each guideline is as follows:

Green = The program has implemented according to the EVMS Standard (ANSI/EIA-748) guideline and the FAA Program Control EVM Assessment Review Criteria.

Yellow = Partially compliant and the program team is obtaining useful program performance data to anticipate and mitigate program risks.  The program has an acceptable action plan.

Red = The program has not implemented according to the EVMS Standard (ANSI/EIA-748 guideline and the FAA Program Control EVM Assessment Review Criteria.

The EVMS Standard (ANSI/EIA-748) guidelines are summarized into five major categories that include related guidelines within each category.

FAA Contractors  EVM System Acceptance Process

The FAA conducts EVMS validation reviews of contractors to verify they have implemented an EVMS as required by the contract and the EVMS Standard (ANSI/EIA-748).  EVMS validation reviews are conducted by the EVM Focal Point in accordance with the FAA EVMS Systems Acceptance Guide and form the basis for formal acceptance of the contractor’s EVMS.  The formal acceptance of the contractor’s EVMS is approved by the Acquisition Executive (ACQ-1) and conveyed by the contracting officer via a Letter of EVM Systems Acceptance and/or Advance Agreement, as applicable.

The EVMS Systems Acceptance Guide defines the process for conducting an EVMS validation review and obtaining acceptance by the contracting officer.  The EVMS Acceptance Guide defines the application and use of initial validation reviews, post acceptance reviews and reviews for cause performed by the EVM Focal Point. The validation review consists of a capability analysis to verify that the proposed EVMS satisfies the guidelines of the EVMS Standard (ANSI/EIA-748) and a review of the EVMS’ use on programs to verify it is being used as designed.

Upon completion of the validation review by the EVM Focal Point and correction of non-compliant areas, as required, the Acquisition Executive approves acceptance of the proposed EVMS and directs the preparation of an Advance Agreement.  The contracting officer issues a Letter of System Acceptance stating that the contractor’s EVMS meets the guidelines of EVMS Standard (ANSI/EIA-748).  FAA also recognizes contractor EVM Systems accepted by DCMA.

When a contractor has a contract with the FAA and employs an EVMS that has been formally accepted by the FAA or DCMA as compliant with FAA’s implementation of  the EVMS Standard (ANSI/EIA-748), the Contracting Officer may recognize the system as being acceptable for other programs.  FAA’s acceptance of the system for other programs depends on the outcome of the EVMS surveillance process.  Because management systems are dynamic due to personnel and other changes, surveillance plays a key role in ensuring the continued integrity of the system.  Without an effective surveillance plan and process, the FAA may not unconditionally accept the EVM system. The EVM Focal Point and the program manager jointly verify and demonstrate to the Acquisition Executive and the contracting officer that the system is being used properly and effectively.

Earned Value Management System Surveillance

Program Performance Surveillance:

AIO in collaboration with Financial Services (ABA) performs AMS EVMS surveillance as part of program-level performance surveillance. The FAA Program Performance Surveillance Guide describes the surveillance process and procedures (insert link to guide).

Contractor EVMS Surveillance:

Program management in coordination with the contracting officer conducts a contractor EVM system surveillance program to ensure the continued integrity of contractor EVM Systems consistent with the contract EVMS requirement.

The FAA Program Performance Surveillance Guide describes the contractor EVMS surveillance process and procedures (insert link to guide).

APPENDIX 1 -- EARNED VALUE MANAGEMENT REFERENCES

FAA guidance on EVM adapts information from various sources, and is not designed as a comprehensive description of EVM activities or practices.  Detailed information on EVM implementation is included in the below references, many of which are available on-line:

ANSI/EIA-748-1998 (Current Version) – Earned Value Management Systems

Defense Contract Management Agency (DCMA) website:  http://www.dcma.mil/

Defense Acquisition University (DAU) Acquisition Community Connection:  http://acc.dau.mil/

Federal Aviation Administration (FAA) IBR Guide

Federal Aviation Administration (FAA) EVMS Surveillance Guide

Federal Aviation Administration (FAA) EVMS Acceptance Guide

FAA Program Control EVM Assessment Review Criteria (Available from the FAA AIO Office)

PMI College of Performance Management website:  http://www.pmi-cpm.org/

Project Management Institute’s (PMI) Guide to the Project Management Body of Knowledge (PMBOK®)