Investment Analysis Risk Guidelines for

Final Investment Decision

#### April 2003

Art Politano

Investment Analysis and Operations Research, ASD-400

Federal Aviation Administration

800 Independence Avenue, SW

Washington, DC 20591

Page Intentionally Left Blank

This document presents the guidelines by which the Investment Analysis (IA) team may conduct Risk Assessments for Final Investment Decisions, as part of the Federal Aviation Administration’s (FAA’s) Acquisition Management System (AMS).  The guidelines were developed to assist IA Teams in their analysis of a preferred alternative.

This risk methodology builds on the IAT Alternatives Risk Assessment for the Initial Investment Decision.  Using these risks as a starting point, the methodology in these guidelines updates the risks and funnels them to the four baseline parameters.  The baseline parameters are cost, benefits, schedule, and performance.  For each of these parameters then, the risk information is used to support risk-adjusted baselines.

We are learning that environmental issues are playing an increasing role in Investment Analysis.  In addition, we recognize that the methodology covered in this report fits acquisition of systems quite well, but facilities not so well.  Accordingly, this methodology should be viewed as an evolving one, and needs to be constantly updated to remain relevant to the context and nature of all Investment Analyses.

Page Intentionally Left Blank

Table of Contents

1.0	Background	1

1.1	Consistency with Revised Policy	1

1.2	Risk Issues are More Critical	1

2.0	Risk for the Initial Investment Decision	2

2.1	History of Risk in Initial Investment Decision Analysis	2

2.2	Focus of Guidelines	2

2.3	Risk Process and Products for Initial Investment Decision	2

3.0	Final Investment Decision Framework	7

3.1	Contracting Implications	7

3.2	Trackable Baselines and Congressional Sanctions	7

4.0	Risk Information Flow Between Initial and Final Investment Decisions	8

4.1	Detailed Risks, Consequences and Mitigation from Initial Investment Decision	9

4.2	Update of Risk Issues	9

4.3	Funneling of All Risks to Baseline Parameters	10

4.4	Assessment for Each Parameter	10

4.5	Integration of Human Factors, Information Security, and Safety Risk Issues	13

5.0	Calculation of Cost, Schedule, Benefit and Performance Risk	14

6.0	Process Integration	16

7.0	Basis of Risk Estimate	16

8.0	Products	16

9.0	Planning for Life Cycle Risk Mitigation	17

10.0	Closure	17

References	18

Appendix:  Standard Basis of Estimate for Risk Analyses	19

# Background

## Consistency with Revised Policy

The Acquisition Management System Policy for Investment Analysis was modified in February 2002.  Investment Analysis was divided into two distinct decision points, the Initial Investment Decision, and the Final Investment Decision.  The Initial Investment Analysis rigorously evaluates alternative solutions to mission need and determines which offers the best value and most benefit to the agency and its customers within acceptable cost and risk.  The Final Investment Analysis develops detailed plan and final requirements for the proposed investment program, including a life cycle program baseline that establishes cost, schedule, performance, benefits parameters, and defines risk-management boundaries for program execution.  While guidelines have been developed and adopted into AMS  (September 2002) for the Initial Investment Decision, no guidelines exist for the Final Investment Decision.  Indeed, there is a great misunderstanding as to how best to assess the risks for a Final Investment Decision.  This paper, then, is designed to provide guidance on how best to conduct a risk assessment for the Final Investment Decision.

The approach builds on the risk information gleaned as part of the Initial Investment Decision.  The approach re-examines the importance of the risk issues identified, updates the risk identification of all issues, frames the assessment to be compatible with human factors, information security, and safety considerations, and, produces a product which strengthens the investment program by facilitating the risk assessment and mitigation in the Solution Implementation and the In-Service Management Phases of AMS.

## Risk Issues are More Critical

Currently, risk assessment is not defined well enough for the Final Investment Analysis.  In the Initial Investment Analysis, the risks and attendant mitigation actions are defined at an aggregate level, e.g., a level specific enough to assist in distinguishing the merits of investment alternatives.  The Acquisition Program Baseline (APB), which  is produced from the Initial Investment Decision, is essentially used as a placeholder to develop a funding wedge for the Acquisition Program.  For the Final Investment Decision, the resulting APB is the basis of a contracted agreement for the FAA to assure the availability of a specific amount of funding for implementing the acquisition.  On the basis of the APB available from the Final Investment Decision, the Integrated Product Team (IPT) is to be able to enter into a contract with a vendor and procure a NAS System.  Should the APB not reflect realistic risk-adjusted costs, then there is a significant risk that the program baselines will be breached.

# Risk for the Initial Investment Decision

## History of Risk in Initial Investment Decision Analysis

The use of risk analysis for FAA Investment Analysis began with the publication of Risk Assessment Guidelines for the Investment Analysis Process in March of 1997.  The Guidelines, in turn, drew heavily from the risk concepts of Acquisition and Program Risk Management Guide, Revision 1, FAA-P-1810 of September 29, 1995.  The Guidelines were revised in 1999, to add human factors, information security, and safety process considerations, and in 2002 to focus their relevance to the Initial Investment Analysis.  The title also changed to Guidelines for Investment Analysis Team’s Alternatives Risk Assessment to reflect the purpose of the effort: to comprehensively examine the range of alternatives under investment consideration.

In September 2002, the 2002 Guidelines were published in the FAA Acquisition Management System Toolset.  They appear in the Investment Analysis Section, under the Standard Guidelines:  http://fast.faa.gov/ams/non_index/investab.htm.  The section also includes: Risk Metrics for the Initial Investment Analysis and the Basis of Estimate for Risk Analysis.

## Focus of Guidelines

In general, within the IA Team’s Alternatives Risk Assessment, there are thirteen facets that constitute an exhaustive range of potential issues, which include: technical, operability, producibility, supportability, benefits estimate, cost estimate, schedule, management, funding, stakeholder, information security, human factors, and safety process.

The Guidelines, given the changing nature of the NAS (National Airspace System) environment, should be taken as dynamic and expected to change in order to keep them relevant to evolving NAS issues.  Most recently, for example, we have learned of the need to add (a) a risk facet focusing on environmental issues, and (b) risk items for facility buildings.  This way, the risk facets and risk checklist would expand the relevance of the methodology to be applicable to a larger range of risk issues.

## Risk Process and Products for Initial Investment Decision

Application of the 2002 Guidelines entails following a deliberate, objective process for identifying and planning for risks.

The initial step is to identify potential risk issues, using a standard risk issues checklist.  In the course of identifying issues, either through research of available written materials or interviews with knowledgeable stakeholders, the IA team often formulates and records preliminary mitigations, and estimates the likelihood of the issue surfacing and the potential severity of the issue.  Stakeholders may include manufactures, operational users, airlines, etc.

The next step may be to convene a team of stakeholders, investment and program analysts, union representatives, and other interested colleagues.  A team comprised of a broad functional-set helps to form an objective assessment.  The team reviews the material and arrives at consensus of each facet’s rating for each alternative by double blind voting (independent votes not visible to others) and justification discussions.  The team also affirms or complements issue mitigations.  At the end of these discussions, the least-risk alternative emerges.

The analyst then coordinates with the cost, benefit, and other analysts to link the impact of the risks and their mitigation on the cost and/or the benefit estimate of the recommended alternative.  This impact contributes to developing ranges around the most likely cost or benefit element in the respective Work Breakdown Structure (WBS).

Discussion with program staff, users, and stakeholders can help identify risk issues.

The products of this effort may be a technical memorandum, provided by the risk assessment team lead, but most often are:

- A stand-alone summary section in the Investment Analysis Report (IAR)

- Solid input for creating cost and benefit high-confidence ranges around the most likely numbers

- Direct input into the Risk Management Matrix in the APB

- Risk Issues Database

The following hypothetical example illustrates the risk assessment products

used for program XXX.  The IA team identified 120 individual risks in the XXX Risk Assessment.  Tables 1 and 2 summarize the criticality of these risks.  Table 1 shows only 68 risks were medium or higher, and of these 7 were high risks.  AMS requires mitigation of all medium or higher risks.  Table 2 identifies risk facets by level of risk.  Funding and information security were assessed as the highest risk.

Table 1:  XXX Risk Facet Rating Matrix

Severity of Impact

36

15

53

Low

1

8

6

Medium

0

0

1

High

Minor

Moderate

Substantial

High

Medium

Low

Key:

Probability of

Adverse Event

Table 2:  Risk Score Summary

| FACET | OVERALL RISK RATING |
| --- | --- |
| Funding | High |
| Schedule | Medium |
| Human Factors | Medium |
| *Safety | Medium |
| Technical | Low |
| Benefits | Low |
| Info Sec | High |
| Management | Medium |
| Operability | Medium |
| Stakeholder | Low |
| Producibility | Low |
| Supportability | Low |
| Cost | Low |
| **Overall Weighted Alternative Risk Score | **Medium |

The Investment Analysis Report for XXX reported:

- Funding-related issues, including inadequate funding and affordability, represent high risks to the XXX program.  Comparison of the XXX program’s life-cycle costs and the Capital Investment Plan (CIP) funding line suggested that XXX could face funding shortfalls in future years.  Any failure to sustain XXX funding could have a substantial impact upon the NAS because XXX is a critical path to modernization.

- Definition of an XXX Build 0 is itself a mitigation strategy to ensure that only the most critical functions are implemented first.  Keeping FAA’s management informed on the criticality and status of the XXX program can also mitigate funding risks.  Other strategies for mitigating funding risk focus on the program office’s management processes:  development of a high-confidence life-cycle cost estimate that takes into account the cost of mitigation strategies provides the program confidence in its baseline.  Establishing financial management systems will provide program management timely information on the status of funds.

- Information security is rated as high risk because of uncertainty associated with unknown potential security requirements changes as a result of the need for increased security.  Other information security issues center around the need for security testing using scanning tools to identify residual risks, and system failure recovery testing.

The risk assessment addressed such high-risk areas as information security and human factors.  Cost ranges were assigned to CLINS such as production, procurement, and deployment to address the additional dollars for software and hardware that would be necessary to increase security and provide redundancy to the XXX system.  Additional risk dollars were added to testing, system engineering, and program management to mitigate risks associated with human factors.

Based on the risks identified, low and high values of variables were entered into Crystal Ball, an analysis software package, to calculate a high-confidence cost estimate.  Crystal Ball uses Monte Carlo simulation, a statistical sampling technique, to incorporate the risk ranges and arrive at a cost estimate considered a high-confidence value.  The high-confidence percentile value was recorded and was used to develop the budget and the APB.

The final product to point out is the risk issue database.  A hypothetical example of a relevant risk issue worksheet is on the following page, as Figure 1.  As Figure 1 shows, the Risk Issue Worksheet summarizes key information, including background, impact, and mitigation aspects.  Background information includes: (a) the risk facet that the issue belongs to, (b) the risk number, (c) the name of identifier of the issue, and (d) a brief description of the issue.  Impact information includes: (a) the probability level of the issue materializing, and (b) the severity of the consequences if the issue materializes.  Mitigation information includes: (a) suggested mitigation strategy, and (b) timing for the mitigation strategy.  Impact information is provided for the risk issue before and after expected implementation of mitigation strategy.

Timing/Dates

5/02 & 1/03

10/02 (SSD Final & SOW)

10/02 (SOW)

TBD

Alternative#1

Substantial

Alternative#1

Medium

Alternative#2

Moderate

Alternative#2

Medium/Low

Alternative#3

Alternative#3

Alternative#2

Substantial

Alternative#2

Medium

Alternative#3

Alternative#3

after proposed mitigation strategy has been implemented

Probability

Alternative#1

High

Probability

Risk Issue # 24

Date:

after proposed mitigation strategy has been implemented

Severity

Alternative#1

Substantial

Severity

Submitted by:

Work Breakdown Structure (WBS) Elements Effected:

Assess SIR 1/2 responses for proposed development and transition approaches and issues.

Define an evolutionary development process that differentiates fundamental or threshold requirements and performance goals and establishes priorities.

Develop and allocate a prospective function or code development “budget” that is schedule-driven and characterizes development potential.

Initiate contingency planning to continue HOCSR to at least 12/2010.

Mitigation Strategy

The proposed HCS replacement date in 2008 and associated precursor activities constrains the time available for development, test and integration.  As acquisition proceedings continue, the amount of software code and functionality that can be reasonably generated in the available time declines.  If required development scope is not effectively managed, then a 2008 operational date will not be achievable.

Risk Identification

RISK FACET: Schedule

Program/Project Title: ERAM

※One Risk Per Worksheet

Timing/Dates

5/0X2 & 1/0X3

10/0X2 (SSD Final & SOW)

Alternative #1

Substantial

Alternative #1

Medium

Alternative #2

Moderate

Alternative #2

Medium/Low

Alternative #3

Alternative #3

Alternative #2

Substantial

Alternative #2

Medium

Alternative #3

Alternative #3

After proposed mitigation strategy has been implemented

Probability

Alternative #1

High

Probability

Risk Issue # 24

Date:

After proposed mitigation strategy has been implemented

Severity

Alternative #1

Substantial

Severity

Submitted by:

Work Breakdown Structure (WBS) Elements Effected:

Assess SIR 1/2 responses for proposed development and transition approaches and issues.

Define an evolutionary development process that differentiates fundamental or threshold requirements and performance goals and establishes priorities.

Mitigation Strategy

As acquisition proceeds, the amount of software code and functionality that can be reasonably generated in the available time declines.  If required development scope is not effectively managed, then an ____2008 operational date will not be achievable.

Risk Identification

RISK FACET: Schedule

Program/Project Title: XXX

※One Risk Per Worksheet

Figure 1: Risk Issues Worksheet

# Final Investment Decision Framework

## Contracting Implications

With the completion of the Initial Investment Decision, the IPT can issue a Request for Offer (RFO) to obtain the market place’s bids for the selected alternative of the potential acquisition.  The Initial APB cannot be used as a basis of awarding a contract because the cost estimate is still at a high aggregate level, lacking detailed specific assumptions.  An RFO, issued after the Initial Investment Analysis is complete, may provide the marketplace’s perspective regarding how reasonable is the costing of the acquisition.

With the completion of the Final Investment Decision, the IPT obtains an FAA commitment to make the funding level identified in the APB available for contract award.  The Final APB becomes the level of funding under which the IPT can enter into a contract.  Without a Final Investment Decision, there is no FAA commitment to fund and a contract cannot be let.

## Trackable Baselines and Congressional Sanctions

With the commitment to fund that comes with a Final Investment Decision, the APB assumes a more important role — that of a yardstick against which the progress is measured.  Baseline breaches of 10% and 50% must be reported to Congress.  Moreover, Congress requires the FAA to consider termination of a program where the breach exceeds 10%, and to terminate programs where the breach exceeds 50%.

To proactively ensure that the APB is as stable as possible, and the breach levels are not exceeded, conservative risk-adjusted estimates are developed for the baselines.  The typical cost baseline developed has a 20% chance of being exceeded.  The typical benefit baseline developed has an 80% chance of being exceeded.

The conservative, risk-adjusted estimates are developed based on the risk issues identified and appraised for cost, benefit, schedule, and performance implications.  The more thorough and solid the risk analysis is, the more likely that the APB will accommodate any uncertainty that develops.  Accordingly, the more likely that the risk issues are anticipated and mitigated, the more likely that the program will succeed.  The role of risk analysis for JRC 2(b) then, is to concentrate the risk focus at a finer level of detail.  This is to ensure that the cost, schedule, benefit, and performance baselines are stable through the anticipation and mitigation of risks.

# Risk Information Flow Between Initial and Final Investment Decisions

The flow of risk information from the Initial Investment Analysis (2(a)) to Final Investment Analysis (2(b)) is best illustrated in the following, Figure 2.  It simply shows that risk information from the Initial Investment Analysis is the basis of the risk assessment for the Final Investment Analysis, along with key inputs from the IPT Programmatic Risk Assessment to arrive at risk for four parameter metrics and interdependency risks.

Figure 2:  Integrated Risk Assessment and Management Approach in Investment Analysis

## Detailed Risks, Consequences and Mitigation from Initial Investment Decision

Out of the Initial Investment Decision (JRC 2(a)), one of the key outputs is the risk issue database for the preferred alternative.  An example can be found in Figure 1.  For each issue identified, there is sufficient background information to understand the likelihood that the issue may materialize, its potential impact, and opportunities for its mitigation.  At the time of the Initial Investment Decision, the technical information available on the preferred alternative is often sketchy so that the risk analysis is, necessarily, at a high level.  The risk assessment in the Initial Investment Analysis is summarized in a 3 by 3 matrix, such as illustrated in Table 1.

## Update of Risk Issues

Following the Initial Investment Decision, the preferred alternative is identified and the work for the Final Investment Decision begins.  The Final Investment Decision affords the IA team more time to examine the preferred alternative.  Correspondingly, it is during this time that the risks are also revisited with respect to the preferred alternative.  Risks are examined more comprehensively and more in depth.

The risk team lead (RTL) for Investment Analysis is responsible for revisiting the risk issues identified in the Initial Investment Analysis to determine if the issues are still relevant, whether the issues have been addressed, or whether other risk issues have come to light on the basis of new information either from secondary sources, users, implementers, the political process, etc. Ideally, the RTL will involve other IA team members from the IPT, sponsors, and users to obtain as objective information as possible regarding the relative importance of the risk issues.

At this stage, issues that are no longer relevant are dropped from further consideration, with appropriate documentation as to why they have been dropped.  In addition, new risk issues that are newly identified now enter the pool for active consideration.  For each new issue identified by the RTL and team, a risk issue worksheet is prepared.

With the update of the risk issues, and the continued advancement of the investment analysis, there is an opportunity for the RTL and the risk team to identify the candidate organizations which may need to be responsible for undertaking mitigation actions.  Assigning responsibility may be a controversial endeavor, and consensus is essential though not critical.  The most prudent basis for assigning responsibility may be  by matching the type of risk that is  to be faced with the functional responsibility of the organization within FAA.  In all cases, an organization should agree to the responsibility and the IA team would also need to endorse such assignment.  Endorsement may be indicated by simply listing the responsible organization along side the risk issues, and schedule for mitigation action in the Risk Management Matrix, which the AMS already requires in the APB.

## Funneling of All Risks to Baseline Parameters

Because of this step, the risk team now has an inventory of risk issues and corresponding worksheet reflecting the most recently available information.  Each risk issue has been uniquely numbered.

During this step, the risk issues are placed in a baseline category that they most influence and are assigned a risk level.

Per the AMS, there are four baseline categories: cost, benefit, schedule, and performance.  Each of the risk issues identified in the last step should now be assigned to a baseline category.  This assignment could be done by the RTL or the risk team.  In either case, the IA team’s cost, benefit, schedule, product team liaison lead, should affirm placement.  Should a risk issue span multiple categories, the issue would be carried in each category.

Moreover, it is also important at this point to consider whether there are any risks of interdependency with other acquisitions in the NAS domain that a proposed acquisition may be in.  For example, a high-capacity surveillance tool may be proposed, but its implementation might depend on the existence of an infrastructure to enable that tool.  The risk of successfully developing an infrastructure would impact the successful development of the surveillance tool.  Interdependency risks, informed by examining the NAS Architecture development waterfall, would also be translated to one of the four parameter baseline categories, if possible.

## Assessment for Each Parameter

Each parameter lead of cost, benefit, schedule, and performance now takes all of the risk issues placed in his/her respective category and, with the help of subject matter experts, assesses the risk level by likelihood of occurrence and by consequence of occurrence according to the criteria presented for each parameter below.

Likelihood of Occurrence Evaluation Criteria

The likelihood of occurrence is defined to be the perceived chance that an identified risk will actually happen.  Five levels of perceived likelihood are proposed for use in risk assessment.  These are identified in the table below.

Consequence of Occurrence Evaluation Criteria

The consequence of occurrence is defined to be the perceived impact on the overall project attribute if an identified risk were actually to occur.  Five levels of perceived consequence of occurrence are proposed for use in risk assessment.  Consequences are rated according to impact on cost, schedule, benefits, and/or technical performance.

Level

Benefits

1

Minimal Impact

2

Minor benefit shortfall,

decrease < 1 %

3

Moderate benefit shortfall,

decrease > 1 % & < 5 %

4

Significant benefit shortfall,

decrease > 5 % & < 30 %

5

Major benefit shortfall,

decrease > 30 %

C

o

n

s

e

q

u

e

n

c

e

For each risk category of cost, schedule, benefit, and performance, all the risk issues are then plotted by their unique number on figure 3.

Figure 3:  Assessment of Risk Issues

All of those issues that are plotted in the “medium” or “high” cells have to be reported on.  The cost, schedule, benefit, and performance leads or experts work with the risk lead and the IPT liaison staff to identify actions that would be necessary to reduce or mitigate the risks.

The cost lead estimates the cost of the mitigation actions and includes the costs in establishing the high-confidence range for the cost baseline.  The benefit lead, the schedule lead, and the performance lead do the same for their part.

If some risks are beyond the control of FAA, then these risk issues may simply have to be acknowledged and accepted, without mitigation.

## Integration of Human Factors, Information Security, and Safety Risk Issues

Risk issues related to key focus areas of concern, e.g., human factors, security (physical and information), and safety management should be worked in co-ordination with the offices responsible for planning in these fields.  The Human Factors Division (AAR-100) of FAA has the expertise to develop human factors risk issues in more detail, and re-assess their impact on acquisitions.  Similarly, the NAS Architecture Branch (ASD-110) has the expertise to assess operational safety risk issues; the Security Systems Engineering Branch (ASD-130) has the expertise to assess security issues.  The RTL and a representative from each of the offices should develop the details for each of the identified risk issues and assess the level of risk (low, medium, and high).  The protocol to be followed in identifying new risk issues, and assessing the impact of risk issues on the success of the acquisition should give preference to the methodologies in place for each Office’s specialty

area.  As a default, the risk checklist used to identify risk issues for the Initial Investment Analysis (see Investment Analysis Teams Alternatives Risk Assessment Guide) should be reviewed to ensure that human factors, information security, and safety are comprehensively reviewed for possible changes in status and relevance.

When the risk assessment comes from the offices responsible for human factors, security, or operational safety, the risk issues that have medium or higher risk level should be identified, as should actions which must be implemented to mitigate the risk issues.  This information is provided to the RTL and, in turn, the RTL provides the information to the cost, benefit, schedule, and performance leads.

With the identified mitigation actions for human factors, security, and operational safety risks, the cost lead estimates the cost of the mitigation actions and includes the costs in establishing the high-confidence range for the cost baseline.  The benefit lead, the schedule lead, and the performance lead do the same for their part of the Investment Analysis.

# Calculation of Cost, Schedule, Benefit and Performance Risk

Figure 4, below, illustrates the general approach in calculation of risk-adjusted numbers for the cost, schedule, benefit, and performance baselines.

Figure 4: Risk Adjustments

Typically, initial calculations are done for each of the baselines on the basis of a model which includes mathematical relationships between variables.

This initial calculations result in a point estimate of the cost, or benefit, or schedule, or performance.

In the course of the risk analysis, mitigation actions are identified or some variable is expected to behave differently than expected.  The change may incrementally add or decrease the value of a variable in the model.  For example:

Cost 	The cost for using a new automation tool may have been identified and considered in the overall cost of an acquisition.  However, a human factors risk may have been identified which concerns the need to train controllers to handle the probable workload adjustment in jointly using the technology (R-side and D-side controllers).  The cost then becomes:

Technical Training Cost + probable increment training cost for effective teaming.

Benefit 	The delay benefit of an automation tool may have been calculated, using national values for growth of airport operations.  However, the local growth rate of operations at an airport are greater than the national rate forecast by FAA.  The benefit then becomes:

Delay reduction based on national growth value + probable incremental delay reduction due to additional reported growth

Schedule	The schedule of a project is calculated to be complete in 5 years, however consultation with software experts has surfaced a concern that given the number of lines of code that are to be developed, a critical software module will take an additional year to complete.  The schedule then becomes:

Schedule as expected + probable additional software development time

Performance	A modernization project is expected to integrate and process xxx surveillance sources, yet because of unexpected development problems only yy surveillance sources can be integrated, and this in turn, will impact the amount of NAS coverage.  Performance then becomes

Coverage with xxx sensors  - probable decrease coverage due to availability

These probable changes in variable values may be many and are all incorporated in establishing the range of estimates around the most likely or the point value of the initial calculations.  Using @ Risk, or Crystal Ball Software tools, the analyst can then create triangular distributions around each independent variable and calculate the dependent variable (overall cost, benefit, schedule or performance).

The tool calculates the dependent variable by randomly drawing a value from the probability distribution of each of the independent variables.  This is done on the basis of a Monte Carlo simulation.  The overall result is itself a calculation with its own distribution.  From this forecast distribution, a value is chosen which corresponds to a high-confidence estimate.  The confidence value will vary by baseline metric:

Cost Value – The value that has an 80 percent certainty of being underrun.

Benefit Value – The value that has an 80 percent certainty of being exceeded.

Schedule Value – The value that has an 80 percent certainty of being underrun.

Performance Value –The value that has an 80 percent certainty of being exceeded.

# Process Integration

Risk assessment for the Final Investment Decision, JRC 2(b), is necessarily an iterative process and reflects a dynamic interplay of IA team members, IPT colleagues for any adjustments to delivery timing and technical content, subject matter experts in specialty engineering to understand the intricacies of the risks and possible mitigation efforts, and cost, benefit, schedule, and performance analysts to conduct risk and sensitivity analysis.

Other colleagues that will have to play a role, of course are users, sponsors, and stakeholders.  Who else might be able to say whether the performance risk is too high or what might be reasonable performance trade-offs.

In applying the risk assessment process for JRC 2(b), it is important to point out that often Investment Analyses come in different levels of complexity, and importance.  Accordingly, it is important to think of the risk assessment process as flexible.  The goal is to always add value, rather than to be a stumbling block or a hurdle.  Larger, more complex projects should certainly get a more detailed analysis than smaller simpler projects.

# Basis of Risk Estimate

In conducting a risk assessment for the final investment decision, it will be critically important to document the basis of estimate for the risk analysis.  A template for the basis of estimate in included in the appendix of this document.

# Products

The APB normally includes risk-adjusted cost, schedule, benefit and performance baselines, on a yearly basis, over the program’s life cycle.

In addition to the risk-adjusted APB, another product which is important to develop is a Risk Management Plan.  The Risk Plan can be part of an element of the Integrated Program Plan or it can be a stand-alone document.

The Risk Plan would identify the steps that would have to be undertaken, the timing of milestones, and the responsible agents, for all risks meeting and exceeding the medium level.  The goal is to demonstrate a commitment to continuously mitigate risks, as identified in Investment Analysis.

Correspondingly, the Risk Plan would also include an element to monitor and track progress in mitigating risk.  The key to risk mitigation status is to show the risk resolution status in comparison with established milestone dates.  This step would be designed to communicate progress to all stakeholders of the program.

Lastly, the Risk Plan would also identify a process for scanning the program’s environment and identifying emerging risks.  This process would be carried out in those phases of AMS following Investment Analysis.

The IPT member of the IA team is the ideal actor in developing the Risk Plan, since the IPT is already responsible for development of the Integrated Program Plan, and the IPT would be responsible for carrying out the next phase of the program’s life cycle, the Solution Implementation phase.

The FAA Programmatic Risk Management Course and Materials provide solid information on risk management and tracking.

# Planning for Life Cycle Risk Mitigation

The phases of AMS following the Investment Analysis phase include Solution Implementation, In-Service Management, and Service Life Extension.  The life cycle of a program will vary, but may be as long as 20 years.  A program will likely always have risks, although the comprehensiveness of the risks and the focus of the risks will vary.  Early in the life cycle, we can expect the risks to cover a broad range of issues, the issues to be treated at the macro level, and the level of uncertainty to be high.  As a program advances through its life cycle, we would expect the range of risk issues to narrow, perhaps focusing on AMS phase-specific issues.  Also, the treatment of those issues would be more focused at a more micro level.

The cost to address program problems increases as the program advances in the life cycle -- a design error is less costly to fix in the design step of a program, rather than during implementation.  Anticipating, mitigating and tracking risk issues gives programs managers an opportunity to reduce unnecessary expenses, and have more control in the success of their programs.  Accordingly, planning and carrying out a risk management plan should be a life cycle long enterprise, because it economically addresses potential problems and keeps a program on the path to success.

# Closure

This report provides guidelines for addressing risk for a program undergoing a Final Investment Decision or JRC 2(b).  The intent of the report has been to advance the treatment of risk with respect to the development of a preferred alternative, and to integrate treatment of risk with the subsequent phases of the AMS following Investment Analysis.

Risk is necessarily a subjective exercise because it deals with uncertainty.  The degree of uncertainty regarding an issue, or the specifics of necessary steps for its mitigation will vary from one colleague to another.  The best way to accommodate the subjective nature of the exercise is to seek a consensus within a broad range of Investment Analysis colleagues, including sponsors, users, implementers, facet area experts, and other stakeholders.  A broad risk analysis team can be expected to self-manage around any tendency toward bias by some individuals.

### References

- Politano, Arturo, Investment Analysis Teams Alternatives Risk Assessment Guide, Federal Aviation Administration, Operations Research and Analysis Branch, August 2002.

- ICIP Course Notes: FAA Programmatic Risk Management, March 2001

#### Appendix:  Standard Basis of Estimate for Risk Analyses

Investment Analysis Standardization Working Group

Usage

In order to maintain a high level of quality for risk analysis conducted in the Initial (JRC 2(a)) or Final (JRC 2(b)), a number of principles must be adhered to in conducting a risk analysis.  These principles are listed below, by Investment Decision.  The risk analyst is encouraged to review these principles before the conduct of the risk analysis, and affirm adherence to them after the completion of the analysis.

General Principles for both Initial (JRC 2 (a)) and Final (JRC 2 (b)) Investment Analyses:

- Risk assessment is done by a risk team whose members are objective and can represent multiple viewpoints and stakeholders.

- Risk mitigation actions are integrated with appropriate cost, benefit, schedule, and other relevant Work Breakdown Structures to facilitate their adoption in the Solution Implementation, and In-Service Management Phases of their life cycle.

Principles for Initial Investment Analysis (JRC 2(a):)

- Findings of the Portfolio Risk Assessment in the Mission Need Analysis phase of AMS are used to inform the risk analysis for the Initial Investment Analysis.

- A common agreed to description of viable alternatives exists.

- The description relates to the given requirements or mission need statement.

- The Risk Assessment team consists of individuals that are very knowledgeable with each risk facet and all alternatives.

- Facet weights are determined prior to evaluation of any alternative to avoid structural bias.  Weights for the reference case may be different than weights for all alternatives.  The rationale for relative weights selected is explained.

- Issues and attendant risks have been identified and commonly acknowledged for each facet.

- The risk score for each investment alternative has been developed independently of other investment alternatives.

- Each team member determines the risk score for each alternative independently of other team members (blind scoring) and writes an explanation for the qualitative or quantitative basis for such scoring.

- The risk team is brought together as a group to discuss and reconcile the team members’ scoring for each alternative.

- Each team member is given an opportunity to consider input from the team and independently rescore risk for each alternative.

- The risk team lead documents the strategy taken to synthesize the scoring into a final rating for each alternative.

- The risk team lead writes a technical memorandum or report which documents the reasons for the risk scores for the most viable candidate, and the actions and strategies which must be employed (including implementation schedule, cost, and performance impacts) to mitigate all medium and high risks.

- The risk assessment results are incorporated in the APB and the Investment Analysis Report consistent with AMS guidelines.

- The risk team lead coordinates with the selected IPT after JRC 2 (a) to facilitate transition of risk issues and information for a more detailed assessment as part of the Final Investment Analysis Decision (JRC 2(b)).

- The results of the risk analysis are made usable in maintaining and updating a NAS-wide portfolio management framework of NAS investments.

Principles for Final Investment Analysis (JRC 2(b)):

- The risk team considers the risk issues identified in JRC 2 (a) as a starting point for the JRC 2 (b) decision and complements this with other available information from the Integrated Product Team.

- The risk team ensures an independent validation of how the risk issue will affect the program’s baseline elements: cost, schedule, benefit, technical performance, and interdependency (with other NAS elements) risks.

- The risk team checks estimates against historical data, such as trade studies, whenever possible.

- Detailed analysis of risk has the following information:

- Technical description

- Related baseline element changes

- Detailed rationale element changes

- Detailed analysis is based on:

- Past performance (actual baseline element changes, e.g., cost/schedule/benefit/performance history) when available

- Discrete estimate (Simulated, scenario analysis, or other approach)

- The risk team determines the tasks on the work breakdown structure (WBS) that could be affected by the risk, and whether the consequences of the risk would require adding tasks that are not on the WBS.

- The Basis of Estimate for Risk Analysis is reviewed for incomplete and or bias implementation.

- The model for quantifying risk is reviewed by subject matter experts (SMEs) to affirm that it is based on the appropriate quantitative analysis techniques based on available data.

- The risk analysis is a probabilistic analysis (whether quantitative or scenario analysis) for the four key APB metrics of cost, schedules, benefits, and performance estimates.

- Correlation between sub components of an APB metric is noted, isolated, and accounted for, by coordination with Cost and Benefit Analysis Teams.

- A risk management plan is prepared to guide risk mitigation and risk monitoring in the Solution Implementation and In-Service Management phases of the AMS.

- The results of the risk analysis are made usable in maintaining and updating a NAS-wide portfolio management framework of NAS investments.