Deployment Planning Process

Flowcharts and Activity Descriptions

- Investment Analysis Activities

- Solution Implementation Activities

- Pre In-Service Decision Activities

- Post In-Service Decision Activities

##### Deployment Planning Process Flowchart

D.5

In-Service Decision

1.0

Investment Analysis

Activities

2.0

Solution Implementation

Activities

3.0

Pre In-Service Decision

Activities

4.0

Post In-Service Decision

Activities

Deployment Planning Process - Definition

Introduction

Deployment planning prepares for and assesses the readiness of a solution to be implemented into the National Airspace System. Deployment planning is part of a continuous In-Service Review (ISR) process that begins early in the lifecycle management process, usually during the development of requirements. All programs undergo some degree of deployment planning to ensure key aspects of fielding a new capability are planned and implemented, as well as to ensure the deployment does not create a critical deficiency in the National Airspace System. The level of authority for  the In-Service Decision (ISD) may vary from the Integrated Product Team Lead to the Joint Resources Council, chaired by the head of the operating line of business.

The conduct of deployment planning involves coordination among and participation of many critical functional disciplines. Trade-offs among cost, schedule, performance, and benefits relative to these functional disciplines must also include the impact of deployment and implementation considerations. Deployment planning tools (such as a tailored In-Service Review checklist) must be used to assist in identifying, documenting, and resolving deployment and implementation issues. Methods and techniques include, but are not limited to, a tailored application of generic tools, the integration of checklist issues with other emerging issues (such as problem test reports from program tests and evaluation), development of action plans for resolution of checklist and other issues, and documentation of decisions and the results of issue resolution and mitigation. Consistent deployment planning must be visible in contractual documents and associated efforts. The results of deployment planning (and issue resolution) activities are briefed periodically (e.g. at Acquisition Reviews), presented at the In-Service Decision meeting, summarized in the ISD Record of Decision, and audited during the post-ISD follow-up and monitoring activities.

Product Teams direct the activities of deployment planning and execution. Sponsoring lines of business monitor product/program deployment planning, provide Product Teams (through team membership) with guidance and technical expertise on ISR issues, and identify additional issues or factors that may affect the ability to field or support the intended product or requirement. In most cases, the NAS Operations Program will represent the sponsoring line of business in deployment planning activities.  All lines of business are accountable to ensure timely resolution and closure of their respective ISR issues.

Deployment Planning Process Flowchart

1.0  Investment Analysis Activities

1.2

Confirm fRD Considerations

D.2

Final Investment Decision

1.1

Establish ISR POC’s

1.3

Confirm IA Considerations

Record

of

Decision

Initial ISR Checklist

# D..1

# Initial Investment Decision

1.4

Establish ISR sub-team.

1.5

Tailor ISR Checklist

Deployment Planning Process

1.0  Investment Analysis Activities

When initiating the investment analysis activities, the In-Service Review (ISR) checklist template is used as a check and balance to ensure that all cost drivers are evaluated, mitigated or dispositioned during the Investment Analysis phase of the product’s life-cycle costing development.  The checklist will be used along with the requirements document to ensure that a comprehensive process of estimating cost drivers is addressed relative to all elements necessary to field an operational system, facility or service.  The Integrated Requirements Team, consisting of cross-functional representatives, will ensure that requirements affecting their functional areas are addressed and/or mitigated.  The ISR Sub-Team is established as a sub-team of the Product Team.  The ISR checklist template is tailored to the specific needs of the product.

| Decision D.1: Initial Investment Decision (JRC-2a) |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Sponsor | Initial Investment Decision | JRC Chair |  |
| Description: The Joint Resource Council (JRC) selects the alternative to be implemented or rejects the alternatives and specifies what action is needed; approves an initial acquisition program baseline for the alternative selected for implementation; approves and funds the action plan for final investment analysis; and designates the integrated product team or management unit responsible for solution implementation. This decision also initiates deployment planning activities. |  |  |  |

| Activity 1.1: Establish Points of Contact |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| IRT Lead IAT Lead |  |  |  |
| Description: Integrated Requirements Team (IRT) and Investment Analysis Team (IAT) Leads will solicit for points of contact from key stakeholders. |  |  |  |

| Activity 1.2: Confirm fRD Considerations |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| IRT Lead |  |  | ISR Checklist Template |
| Description: Ensure Integrated Requirements Team uses the ISR checklist template. Confirm elements of checklist have been considered in the requirements. |  |  |  |

| Activity 1.3: Confirm IA Considerations |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| IAT Lead |  |  | ISR Checklist Template |
| Description: Ensure Investment Analysis Team uses the ISR checklist template. Confirm elements of the checklist have been considered in the investment analysis. |  |  |  |

| Activity 1.4: Establish ISR Team |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Product Team Lead |  |  | Product Team Charter/Plan, ASP and IPP Templates |
| Description: The ISR Sub-Team is a sub-team of the Product Team (PT) as described in the Product Team Charter/Plan. The ISR Sub-Team is composed of appropriate organizations to represent their respective ISR element. The ISR Sub-Team remains in place until all actions in the In-Service Decision Action Plan are closed. The strategy for conducting the deployment planning process is included in the Acquisition Strategy Paper (ASP). The deployment planning process activities, as related to the product, are defined in the Integrated Product Plan (IPP). |  |  |  |

| Activity 1.5: Tailor ISR Checklist |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team | Initial ISR Checklist |  | ISR Checklist Template |
| Description: Using the ISR checklist template, ensure all ISR elements are identified and tailor the checklist based on the requirements in the final Requirements Document (fRD). Assign checklist item ownership. |  |  |  |

| Decision D.2: Final Investment Decision (JRC-2b) |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ACM | Record of Decision | FAA Acquisition Executive |  |
| Description: At the Final Investment Decision, the Joint Resources Council designates the In-Service Decision authority. This is based on the recommendation of the sponsoring organization. If the Joint Resources Council retains the In-Service Decision authority, the chair is the Associate Administrator for the operating organization. For programs already in Solution Implementation, the Associate Administrator for the operating organization designates the In-Service Decision authority. For those programs designated for Independent Operational Test and Evaluation (IOT&E), the IOT&E designation process may also establish the In-Service Decision authority. ACM prepares the Record of Decision that includes the designation of the In-Service Decision authority. |  |  |  |

Deployment Planning Process Flowchart

2.0 Solution Implementation Activities

2.1

Update

ISR

Checklist

2.2

Checklist Status

Review

D..3

Ready to Begin  Prep for ISD?

Deployment Planning Status Report

Updated

ISR

Checklist

2.3

Prepare Pre-ISD Action

Plan

2.4  Coordinate with Stakeholders

Pre-ISD

Action

Plan

## N

## Y

From

D.2

Deployment Planning Process

2.0 Solution Implementation Activities

During solution implementation, the product team routinely reviews and updates the ISR checklist, and reports the status of deployment planning activities.

| Activity 2.1: Update ISR Checklist |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team | Updated ISR Checklist |  |  |
| Description: The ISR Sub-Team routinely reviews and updates the status of the ISR checklist. This includes coordinating, resolving and validating closure with stakeholders. Non-routine updating of the checklist can occur when program changes may result in adding or deleting checklist issues. Disciplined control of the ISR checklist will be accomplished by assigning version control and maintaining a case file. |  |  |  |

| Activity 2.2: ISR Checklist Status Review |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team Product Team Lead | Deployment Planning Activities Status Report; Acquisition Review Briefing | Product Team Lead | Deployment Planning Activities Status Template; Acquisition Review Briefing Format |
| Description: The ISR Sub-Team prepares the deployment planning activities status report for program management reviews. The status is intended to identify the high-risk issues and the actions needed for successful closure. In addition, the product team lead will present deployment-related issues at Acquisition Reviews when discussing risk management. |  |  |  |

| Decision D.3: Ready to Begin Preparation for ISD? |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team |  | Product Team Lead |  |
| Description: The ISR Sub-Team assesses the risks associated with open ISR checklist issues. The ISR Sub-Team meets with the ISD Secretariat to begin preparation for the ISD meeting. The Product Team Lead determines that the product is ready to begin preparation for the ISD meeting. If the product is not ready, the ISR Sub-Team continues to resolve and close open issues. |  |  |  |

| Activity 2.3: Prepare Pre-ISD Action Plan |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team | Pre-ISD Action Plan |  | ISD Action Plan Template |
| Description: The ISR Sub-Team will prepare the preliminary ISD Action Plan to document the commitments to complete open deployment issues. The plan will include open ISR checklist, test and evaluation, union, and other issues. The plan will include, as a minimum, action office and closing authority organizations, completion date, and funding needed for the successful accomplishment of open issues. Note: Preparation of the plan will be approximately 80 percent complete at this point. It is anticipated that additional actions will be identified through stakeholder coordination and the IOT&E Report. |  |  |  |

| Activity 2.4: Coordinate with Stakeholders |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Product Team Lead/ Sponsor |  | Sponsor |  |
| Description: The Product Team Lead will brief and coordinate the status of the product and identify and assign action for resolution of deployment critical issues. This activity will ensure that issues are identified and action plans are prepared to resolve issues at the appropriate level prior to the ISD meeting. The Product Team Lead is responsible for obtaining stakeholder concurrence on closure or proposed resolution of these issues. The Sponsor is responsible for engaging with the product team to reach agreement on resolution. In most cases, the ATP organization is the closing authority for Air Traffic operational issues; and the AOP organization is the closing authority for Airway Facilities operational issues. If necessary, issues may be elevated to the Integrated Product Team Lead/Program Director level for resolution. |  |  |  |

Deployment Planning Process Flowchart

3.0 Pre In-Service Decision Activities

3.2

Develop ISD Briefing

3.1

Complete

ISD Action Plan

D.4 Ready for ISD?

3.5

Hold ISD

Meeting

3.4

Hold Stakeholders’ Meeting

3.3

Schedule

Stakeholder and

ISD

Meetings

# Y

From

2.4

ISD Action

Plan

Draft ISD Briefing

Go to D.5

Go to  2.4

Final

ISD Briefing

N

Deployment Planning Process

3.0 Pre In-Service Decision Activities

The preliminary In-Service Decision activities of the deployment planning process focus on preparation for the In-Service Decision (ISD) meeting.  Two documents must be prepared in advance of the meeting: the proposed ISD Action Plan and the ISD Briefing.

In preparing for the ISD meeting and the briefing, it is important to keep perspective.  The Product Team's role and responsibility is to obtain the In-Service Decision. The Sponsor's role and responsibility is to make the decision.

The NAS In-Service Management Division, AOP-1000, serves as the secretariat for the In-Service Decision authority.

| Decision D.4: Ready for ISD? |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Product Team Lead with Sponsor Support |  |  |  |
| Description: At this point, the Product Team Lead coordinates with the ISD Secretariat, and the decision is made as to the readiness of a product for the In-Service Decision. This decision is based on an evaluation of the ISR checklist, action plans and remaining unresolved issues. The Product Team Lead is responsible for obtaining stakeholder concurrence on closure or resolution of these issues. The Sponsor is responsible for engaging with the product team to reach resolution. |  |  |  |

| Activity 3.1: Complete ISD Action Plan |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team | Pre-ISD Action Plan | Product Team Lead | ISD Action Plan Template |
| Description: Prepare the ISD Action Plan(s) per the outcome of the initial stakeholder review and coordination, IOT&E*, and the decision on the closure of the open issues. The ISD Action Plan(s) will not contain unrecoverable issues, and on presentation to the ISD authority, will contain signatures of the action office and closing authority organizations. See Activity 2.3, Prepare Pre-ISD Action Plan. *IOT&E inputs to the ISD Action Plan are independent of Product Team Lead approval. |  |  |  |

| Activity 3.2: Develop ISD Briefing |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team | Draft ISD Briefing | Product Team Lead | ISD Briefing Template |
| Description: The ISR Sub-Team prepares the ISD briefing incorporating the ISD action plan(s). Summarizes program status, and identifies all issues relevant to the ISD. *IOT&E inputs to ISD Action Plan are independent of Product Team Lead approval. |  |  |  |

| Activity 3.3: Schedule Stakeholder and ISD Meetings |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| AOP-1000 | Draft ISD Briefing |  |  |
| Description: The NAS In-Service Management Division, AOP-1000, serves as the secretariat for the In-Service Decision authority. AOP-1000 will schedule the stakeholders’ and ISD meetings. Prior to the ISD meeting, AOP-1000 provides advisory and liaison support to determine readiness for the ISD meeting. In addition, meeting dates are coordinated and determined for attendees, rooms are reserved, logistics arranged, and attendance managed. Meetings will be scheduled around the calendar of the designated In-Service Decision authority. Changes in the schedule are coordinated in the same manner. Attendees will be notified of the meeting and any changes. At least two weeks prior to holding the ISD meeting, the Product Team Lead contacts AOP-1000 to schedule the stakeholder and ISD meetings, and provides an electronic copy of the draft ISD briefing and copies of signed ISD action plans. |  |  |  |

| Activity 3.4: Hold Stakeholders’ Meeting |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Product Team Lead/ Sponsor | Final ISD Briefing | Stakeholders | ISD Briefing Template |
| Description: The Product Team Lead and Sponsor conduct final coordination with stakeholders to obtain concurrence on the ISD briefing and ISD action plan(s). Coordinate changes/updates to the briefing. Produce the final ISD briefing. |  |  |  |

| Activity 3.5: Hold ISD Meeting |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Product Team Lead/ Sponsor |  |  |  |
| Description: The Product Team Lead and Sponsor will jointly present the ISD briefing to the designated ISD authority, the intent being to give all parties an opportunity to provide their input. The Sponsor can be decided internally within the Sponsor's team, as appropriate, and in coordination with the rest of the Product Team. The Product Team Lead will provide copies of the ISD briefing to meeting attendees. |  |  |  |

Deployment Planning Process Flowchart

4.0 Post In-Service Decision Activities

D.6

ISD Action Plan Complete?

4.2

Execute

Plan/ Report Status

## N

4.1

Finalize

ISD Documentation

D.5

ISD?

# Y

Done

Record of Decision

ISD

Closeout Memo

ISD

Action Plan Status

Report

Go To

2.4

Final

ISD

Action

Plan

4.3

Notify

ISD

Authority

Y

###### From 3.5

N

Deployment Planning Process

4.0  Post In-Service Decision Activities

The post In-Service Decision activities focus on documenting the In-Service Decision, establishing a periodic review, and tracking progress of completing the ISD Action Plan.  The Record of Decision is prepared to document  the results of the In-Service Decision meeting.  The ISD Action Plan is included as an attachment to the Record of Decision.  The ISD Action Plan is tracked and progress is reported at periodic reviews (i.e., Acquisition Reviews and other appropriate management reviews).  The ISD authority is notified when the ISD Action Plan has been completed.

| Decision D5: In-Service Decision (ISD) |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Designated ISD Authority |  | Designated ISD Authority |  |
| Description: The designated ISD authority approves the deployment of the product into the NAS. If the decision is “yes”, the Record of Decision and ISD Action Plan are finalized and the review and tracking process for the ISD Action Plan is initiated. If the decision is “no”, actions are initiated to resolve or correct identified issues. See Activity 2.4, Coordinate with Stakeholders. |  |  |  |

| Activity 4.1: Finalize ISD Documentation |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| AOP-1000 with Product Team Lead Support | Record of Decision Final ISD Action Plan | Designated ISD Authority | Record of Decision Template ISD Action Plan Template |
| Description: Prepare the Record of Decision to document the decision made at the ISD meeting. Incorporate any changes to the ISD Action Plan and include the plan as an attachment to the Record of Decision. Obtain the signature of the designated ISD authority and distribute the final documentation. Maintain official files. |  |  |  |

| Activity 4.2: Execute Plan/Report Status |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| Product Team Lead ISR Sub-Team | ISD Action Plan Status Report |  | ISD Action Plan Status Report Template |
| Description: Execute the ISD Action Plan. Update and report the status of completing the ISD Action Plan at Acquisition Reviews and other appropriate management reviews. |  |  |  |

| Decision D.6: ISD Action Plan Complete? |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| ISR Sub-Team with AOP-1000 Support |  | Individual Closing Authority for Action Plan |  |
| Description: If the decision is “yes’, notify the designated ISD authority. If the decision is “no”, continue to execute the ISD Action Plan, update and report the status. |  |  |  |

| Activity 4.3 Notify ISD Authority |  |  |  |
| --- | --- | --- | --- |
| Responsible Agent | Product | Approval Authority | Tools/Aids |
| PT Lead with AOP-1000 Support | ISD Closeout Memorandum |  | ISD Closeout Memorandum Template |
| Description: Prepare ISD Closeout Memorandum and coordinate through AOP-1000 in order to notify the designated ISD authority that the ISD Action Plan has been completed. |  |  |  |

DEPLOYMENT PLANNING PROCESS TEMPLATES

- In-Service Review Checklist Template

- Deployment Planning Activities Status Report

- In-Service Decision Briefing

- Record of Decision

- In-Service Decision Action Plan

- In-Service Decision Action Plan Status Report

- In-Service Decision Closeout Memorandum

Link to In-Service Review Checklist Template

Deployment Planning Activities Status Report Template

# Use this template to report status at Program Reviews.
 
DEPLOYMENT PLANNING ACTIVITIES

## Summarize Preliminary Deployment Planning Activities

### Have the roles and responsibilities of the ISR team been included in the team plan/charter?

### Have the strategies for conducting deployment planning activities been included in the Acquisition Strategy Paper?

### Have the deployment planning activities been described in the Integrated Product Plan?

### Has the ISR checklist template been tailored and baselined? When?

## ISR Checklist Last Updated				<Date>

## Results of Latest Update

#### ISR Checklist Issues Identified			<Number>

#### ISR Checklist Issues Open			<Number>

#### ISR Checklist Issues Closed			<Number>

## Planned Date for In-Service Decision		<Date>

## Designated In-Service Decision Authority	<AXX-1>

## Issue(s): Discuss high-risk issue(s) and action(s) required.

# In-Service Decision Briefing Template

# REQUEST FOR IN-SERVICE DECISION FOR 

<NAME OF PRODUCT>

<DATE>

## <Name of Product Team Lead>

<Name of Sponsor’s Lead >

# AGENDA

## OVERVIEW

## COST BASELINE

## SCHEDULE BASELINE

## SUMMARY OF OPEN ISSUES

## REVIEW OF IN-SERVICE DECISION ACTION PLAN

## RECOMMENDATION

## POST IN-SERVICE DECISION ACTIVITIES

# OVERVIEW

## Identify the Mission Need.

## Briefly describe the product or solution.

## Limit overview to one page.

## Use bullet format.

# COST BASELINE

## Show the latest approved cost baseline including historical lifecycle costs as well as future lifecycle costs.

## Use the format of Table 2.1, Cost Baseline, of the Acquisition Program Baseline guidance (see FAST).

# SCHEDULE BASELINE

## Show the latest approved schedule baseline.

## Use the appropriate categories and events described in Exhibit 1, Sample Schedule Baseline Categories and Events, under Performance Baseline of the Acquisition Program Baseline guidance (see FAST).

# SUMMARY OF IDENTIFIED ISSUES

## ISR Checklist Issues Identified				[Number]

## ISR Checklist Issues Closed					[Number]

## ISR Checklist Issues Open	 				[Number]

## IOT&E Issues Identified 						[Number]

## IOT&E Issues Closed						[Number]

## IOT&E Issues Open							[Number]

## Other Issues Identified						[Number]

## Other Issues Closed						[Number]

## Other Issues Open	 						[Number]

#### SUMMARY OF OPEN ISSUES BY RISK LEVEL

# IN-SERVICE DECISION ACTION PLAN

## ISSUE:  Describe the issue that must be resolved.

## SOURCE OF ISSUE: Identify source of issue.  Issues may generate from the ISR Checklist, IOT&E, union, In-Service Decision, or other source.

## ACTION REQUIRED: Describe the action needed and the criteria to be met to resolve the issue.  Milestones may be used.

## RISK LEVEL:  Specify High/Medium/Low Risk Level.

### (See FAST guidance relating to Acquisition Program Baseline Risk Management.)

## FUNDING: Identify funding needed or available funding source for completion of action.

## PLANNED COMPLETION DATE: Establish the planned date for completion of action.

## ACTION OFFICE: Identify the organization(s) that will complete action.

## CLOSING AUTHORITY: Identify the organization(s) that will determine that the issue has been resolved.

## SIGNATURES REQUIRED: Obtain the signature(s) of the action office and the closing authority organizations.

# RECOMMENDATION

## Recommend appropriate In-Service Decision.

## Discuss impacts, if In-Service Decision is not made.

# POST IN-SERVICE DECISION ACTIVITIES

## Describe Post In-Service Decision activities

### Discuss plan for periodic reporting on the status of ISD Action Plan at Acquisition Reviews and other management reviews

### Discuss plan for updating ISD Action Plan

### Discuss plan for submitting the ISD closeout memorandum

Record of Decision Template

RECORD OF In-Service Decision

for product

Date of Decision

This is the template to use to document the In-Service Decision.

Discussion

State the purpose of the meeting

Include the name of sponsor (AOP) requesting the in-service decision.

Identify the presenter(s) and their area of expertise.

List the names/organizations of attendees.

Summarize the technical, schedule, and cost status.

Summarize the open issues presented in the ISD Action Plan.  Highlight Independent Operational Test and Evaluation (IOT&E) recommendations and union concerns.

Summarize other considerations, e.g., political, international.

Summarize significant comments made by attendees. Decisions

## Decision

State deployment decision made by the ISD authority.

List specific direction provided by the ISD Authority.

List action items assigned by the ISD authority.  Examples include specific actions to be completed before delivering additional systems or before Initial Operating Capability.

Describe Post In-Service Decision activities to establish a periodic review and tracking process for the ISD Action Plan.  Include periodic reporting on the status of the ISD Action Plan at Acquisition Review and other management reviews; and submitting the ISD closeout memorandum.

Approved:

/Signature/

Name of decision authority

Office of the decision authority

Attachment:  ISD Action Plans

In-Service Decision Action Plan Template

Use this template to prepare an action plan for each issue.

ISSUE:  Describe the issue that must be resolved.

SOURCE OF ISSUE: Identify source of issue.  Issues may generate from the ISR Checklist, IOT&E, Union, ISD, or other appropriate source.

ACTION REQUIRED: Describe the action needed and the criteria to be met to resolve the issue.  Milestones may be used.

RISK LEVEL:  Specify high/medium/low risk level.  (See FAST guidance relating to Acquisition Program Baseline Risk Management).

FUNDING: Identify funding needed or available funding source for completion of action.

PLANNED COMPLETION DATE: Establish the planned date for completion of the action.

ACTION OFFICE: Identify the organization (s) that will complete the action.

CLOSING AUTHORITY: Identify the organization(s) that will determine that the issue has been resolved.

SIGNATURES REQUIRED: Obtain the signature(s) of the action office and the closing authority organizations.

# Use this template to report status at Management Reviews.
 
IN-SERVICE DECISION ACTION PLAN STATUS REPORT

## In-Service Decision						<Date>

## Designated In-Service Decision Authority

## ISD Action Plan Last Updated				<Date>

## Results of Latest Update

###  Action Plan Issues Identified			<Number>

###  Action Plan Issues Open				<Number>

###  Action Plan Issues Closed				<Number>

## Issue(s):  Describe high-risk issue(s) and action(s) required.

## Planned Closeout 						<Date>

In-Service Decision Closeout Memorandum Template

Memorandum

US Department

of Transportation

Federal Aviation

Administration

| Subject: | INFORMATION: Closeout of In-Service Decision Action Plan for Product Generator Replacement Project (E-G Oiwer |  | Date: | # Insert Date |
| --- | --- | --- | --- | --- |
| From: | # Sponsor/AOP and Product Team Lead | Reply to Attn. of: |  |  |
| To: | # In-Service Decision Authority |  |  |  |

This memorandum documents the completion of the Post In-Service Decision activity for PRODUCT.  The In-Service Decision (ISD) Action Plan for PRODUCT  has been completed.  The completion date for each issue is recorded in the attached ISD Action Plan Report.  Signatures are on file from the closing authority to document the satisfactory resolution of issues.

/Signature/                                                            /Signature/

## Sponsor/AOP                                    		Product Team Lead

Attachment:

ISD Action Plan Report