ATTACHMENT B

Lease No: DTFA    -    - L -

The purpose of this ATTACHMENT B is to define and describe the processes which both the Lessor and the Government shall complete in order to design and build-out the Tenant Improvements.

PART I – TENANT IMPROVEMENTS AND TENANT IMPROVEMENT ALLOWANCE

  - – TENANT IMPROVEMENTS (10/12)

- The Tenant Improvement Allowance is $<insert dollar amount per foot> per ANSI/BOMA Office Area square foot which shall be paid entirely by Lessor, including any instance where the Government accepts fixtures and/or other Tenant Improvements already in place. Tenant improvements are the components, finishes, and fixtures that typically take space from the “shell” condition to a finished, usable condition. The Tenant Improvement Allowance shall cover all or a portion of the cost of the design and build out of the Government-demised area in accordance with the Government-approved Design Intent Drawings and the Tenant Improvements Price Proposal (refer to PART II – DESIGN, CONSTRUCTION – Paragraph 2.10) – (hereafter described as “cost of the design and build out”). If the cost of the design and build out is in excess of the Tenant Improvement Allowance, refer to paragraph 1.2. All Tenant Improvements required by the Government for occupancy shall be constructed and paid for by the Lessor as part of the rental consideration, and all improvements shall meet the quality standards and requirements of this solicitation and its attachments. At no additional cost to the Government, the Lessor agrees to pay and disburse all the tenant improvement payments, and provide the Government with all costs associated with the tenant improvements including, but not limited to, construction costs and costs related to preparation of construction plans, construction management fees, city fees and permit costs or penalties, certificate of occupancy and applicable taxes and engineering fees.

- The Government, at its sole discretion, shall make all decisions as to the usage of the Tenant Improvement Allowance. The Government may use all or part of the Tenant Improvement Allowance. The Government may return to the Lessor any unused portion of the Tenant Improvement Allowance in exchange for a decrease in rent. If applicable, the principal amount of the cost of the Tenant Improvements in excess of the Tenant Improvement Allowance as described herein below under Section 1.2, Paragraph A, item 3) - shall be adjusted (reduced) based on the amount of any unused portion of the Tenant Improvement cost.

See paragraph 1.2 for information on “Lessor’s Recovery of Tenant Improvement Costs in Excess of the Allowance.”

- The Tenant Improvement Allowance shall include all of the Lessor’s administrative costs, general contractor fees, subcontractor’s profit and overhead costs, Lessor's profit and overhead, design costs, and other associated project fees necessary to prepare construction documents and to complete the tenant improvements. It is the Lessor’s responsibility to prepare all documentation (working/construction drawings, etc.) required to receive construction permits. NO COSTS ASSOCIATED WITH THE BUILDING SHELL SHALL BE INCLUDED IN THE TENANT IMPROVEMENT PRICING.

- If the Government determines that termination of the lease is in the best interest of the Government, the Government shall pay an amount based on the unamortized balance of the Tenant Improvement Allowance as of the first day of the month the lease is cancelled and terminated, as described in 1.3 ‘Lessor’s Recovery of Tenant Improvement Allowance in the Event of Cancellation’ below.

  - – LESSOR’S RECOVERY OF TENANT IMPROVEMENT COSTS IN EXCESS OF THE ALLOWANCE (10/12)

- If the Government build costs are in excess of $<insert dollar amount per foot> per square foot or $<insert dollar amount> the Government reserves the right to either: 1) reduce the Tenant Improvement requirements, 2) pay a lump sum for the overage amount upon completion and acceptance of the improvements, or 3) increase the rent to cover the amount in excess of the allowance according to the negotiated amortization rate over the term of the lease. Reimbursement shall occur only after acceptance of the space, and shall be based on a detailed invoice provided by the Lessor and the determination by the Real Estate Contracting Officer that the work completed is satisfactory; such determination to take place only after an inspection of the work and building materials by the Real Estate Contracting Officer.

- Notwithstanding the foregoing, at Government’s option, Lessor shall fund an additional amount for Government’s cost of installing security systems, computer wiring, and telephone wiring up to a maximum additional amount not to exceed $<insert dollar amount>; and the Government shall reimburse Lessor within <insert # of business days> business days of acceptance of such systems and wiring in writing and executed by the Real Estate Contracting Officer, based upon a detailed invoice provided by Lessor. If the Government installs its own security systems, computer wiring, or telephone wiring, the Government covenants that the Lessor shall have no liability regarding these installations.

  - – LESSOR’S RECOVERY OF TENANT IMPROVEMENT ALLOWANCE IN THE EVENT OF CANCELLATION (10/12)

The Lessor shall recover the unamortized balance of the tenant improvement allowance (or a lesser amount as described in the following sentence), effective on the date of cancellation. The Lessor shall amortize the actual cost of the tenant improvement or the tenant improvement allowance, whichever amount is less, over the term of the lease. The Lessor shall make a disclosure of all tenant improvement costs to the Government after all tenant improvement costs have been accounted for, such disclosure shall include a monthly payment schedule of said tenant improvement costs and balance remaining each month. In the event that the Government cancels this lease, or any portion thereof: the Government agrees that it shall make a one-time, lump sum payment to the Lessor for the remaining balance of tenant improvements costs in their entirety if the entire lease is terminated, or prorate, if any portion thereof is cancelled. Lessor agrees that such payment shall release the Government from all present and future liability under this clause.

  - – AMORTIZATION SCHEDULE (10/12)

The Lessor is required to complete the amortization payment schedule for the following: 1) if the Government build-out is in excess of the tenant improvement allowance or 2) in the event of an early lease termination. The amortization is based on a <insert interest rate>% (interest agreed on the tenant improvement) rate of return, with payments of $<insert dollar amount> per month in arrears as follows:

Lessor shall fill in the “Tenant and Associated Fees Amortization Schedule”

Total Amortization:	$<insert dollar amount>

Annual Interest Rate: 	<insert interest rate>%

Terms in Years: 	<insert # of years>

Payments Per Year:	<insert # of payments>

PART II – DESIGN, CONSTRUCTION

  - – WORK PERFORMANCE (7/10)

All work in performance of this lease shall be done by skilled workers or mechanics and shall be acceptable to the Real Estate Contracting Officer. The Real Estate Contracting Officer retains the right to reject the Lessor’s workers 1) if such are either unlicensed, unskilled, or otherwise incompetent, or 2) if such have demonstrated unacceptable performance in connection with work carried out in conjunction with this lease. In the event of such rejection, the Lessor shall offer substitute/replacement workers, subject to the approval of the Real Estate Contracting Officer.

  - – RESPONSIBILITY OF THE LESSOR AND LESSOR’S ARCHITECT/ENGINEER (10/12)

- The Lessor shall be responsible for the professional quality, technical accuracy, and the coordination of all designs, drawings, specifications, and other services furnished by the Lessor under this contract. The Lessor shall, without additional compensation, correct or revise any errors or deficiencies in its designs, drawings, specifications or other services.

- The Lessor remains solely responsible for designing, constructing, operating, and maintaining the leased premises in full accordance with the requirements of the lease. The Government retains the right to review and approve many aspects of the Lessor’s design, including without limitation, review of the Lessor’s design and construction drawings, shop drawings, product data, finish samples, and completed Base Building and Tenant Improvement construction. The Government shall work closely with the Lessor, in an integrated manner, to identify potential design flaws, to minimize costly misdirection of effort, and to assist the Lessor in its effort to monitor whether such design and construction comply with applicable laws and satisfy all Lease requirements.

- Neither the Government’s review, approval or acceptance of, nor payment through rent of the services required under this contract, shall be construed to operate as a waiver of any rights under this contract or of any cause of action arising out of the performance of this contract, and the Lessor shall be and remain liable to the Government in accordance with applicable law for all damages to the Government caused by the Lessor’s negligent performance of any of the services required under this contract.

- Design and construction and performance information is contained throughout several of the documents which shall comprise a resulting lease. The Lessor shall provide to space planners, architects, engineers, construction contractors, etc., all design and performance information required whether it is found in the submitted SFO, the lease attachments, Price Lists, or Design Intent Drawings. Reliance upon one of these documents to the exclusion of any other may result in an incomplete understanding of the scope of the work to be performed and/or services to be provided.

  - – LIQUIDATED DAMAGES (7/10)

In case of failure on the part of the Lessor to complete the work within the time fixed in the lease contract, the Lessor shall pay the Government as fixed and agreed liquidated damages, pursuant to this paragraph, the sum of $<insert dollar amount> for each and every calendar day that the delivery is delayed beyond the date specified for delivery of all the space ready for occupancy by the Government. This remedy is not exclusive and is in addition to any other remedies which may be available under this lease or at law. This liquidated sum is not meant as a penalty, but as an approximation of actual damages that would be suffered by the Government as a result of the Lessor’s delay.

  - – CONSTRUCTION WASTE MANAGEMENT (10/12)

- Recycling construction waste generated by any and all forms of space alteration for tenant improvements required by the lease is mandatory.

- Recycling construction waste means providing all services necessary to furnish construction materials or wastes to organizations which shall employ these materials or wastes in the production of new materials. Recycling includes the labor and equipment required to separate individual materials from the assemblies of which they form a part.

- The Lessor shall reuse all waste items resulting from alteration or renovation to the extent possible. If waste items are not suitable for reuse in the new tenant improvements then such items should be recycled accordingly. During the demolition and construction phases of any alteration project pertaining to the leased space, the Lessor shall recycle the following items, subject to economic evaluation and feasibility:

- Ceiling grid and tile;

- Light fixtures, including proper disposal of any transformers, ballasts, and fluorescent light bulbs;

- Duct work and HVAC equipment;

- Wiring and electrical equipment;

- Aluminum and/or steel doors and frames;

- Hardware;

- Drywall;

- Steel studs;

- Carpet, carpet backing, and carpet padding;

- Wood;

- Insulation;

- Cardboard packaging;

- Pallets;

- Windows and glazing materials;

- All miscellaneous metals (as in steel support frames for filing equipment); and

- All other finish and construction materials.

- If any waste materials encountered during the demolition or construction phase are found to contain lead, asbestos, polychlorinated biphenyls (PCB's) (such as fluorescent lamp ballasts), or other harmful substances, they shall be handled and removed in accordance with federal and state laws and requirements concerning hazardous waste.

- In addition to providing "one time" removal and recycling of large scale demolition items such as carpeting or drywall, the Lessor shall provide continuous facilities for the recycling of incidental construction waste during the initial construction.

  - – LESSOR’S UNIT PRICES/COSTS AND CONSTRUCTION SCHEDULE (10/12)

Within <insert # of business days> business days after award of the lease contract, the Lessor shall submit to the Real Estate Contracting Officer (A) a detailed description of unit prices/costs and (B) a tentative construction schedule giving the dates on which the various phases of construction shall be completed to coincide with the Government's required occupancy date. (Refer to the "Occupancy Date" paragraph in ‘PART II - DESCRIPTION OF REQUIREMENTS’ section of the submitted SFO). The finalized schedule shall be submitted no later than <insert # of business days> business days after award. The schedule shall include timing for completion of design and construction milestones including, but not limited to: 1) submittal of preliminary plans and specifications; 2) submittal of other working drawings; 3) Real Estate Contracting Officer’s approval of completed construction documents and the Tenant Improvements Price Proposal (reference 2.10 below); 4) issuance of any and all required building permits; 5) start of construction; 6) completion of principal categories of work; 7) phased completion and availability for occupancy of each portion of the Government-demised area (by floor, block, or other appropriate category); 8) final construction completion; and 9) inspection and acceptance of the Leased Premises by the Government.

  - – CONSTRUCTION SCHEDULE AND ACCEPTANCE OF TENANT IMPROVEMENTS (10/12)

The construction schedule shall commence upon lease award, unless otherwise expressly agreed by the Lessor and Government as stated in the lease. The schedule shall be divided into seven tasks for each phase. These are: 1) the generation of the Design Intent Drawings; 2) the Government’s approval of the Design Intent Drawings; 3) the Lessor’s generation of the Government’s construction documents; 4) the Government’s review and approval of the construction documents; 5) the submittal of the Tenant Improvements Price Proposal (reference to paragraph 2.10 below), Government’s review, approval, and Notice to Proceed (NTP) process; 6) the Lessor’s construction of the leased premises; and 7) the Government’s acceptance of the space upon completion of construction. References to “approval” shall mean such approval granted by the Real Estate Contracting Officer in writing. During the construction schedule, the Government may require regularly scheduled progress meetings and that the Lessor keep meeting minutes of discussion topics and attendance. During the design and construction tasks, the Lessor may discover instances where the Government’s directives conflict. In such cases, the Lessor shall immediately notify the Real Estate Contracting Officer in writing so that the Government may issue a determination as to how to proceed.

  - – DESIGN INTENT DRAWINGS (10/12)

The Design Intent Drawings (also known as “Preliminary Drawings” or “Prelims”) will either be prepared by the Lessor or the Government, as determined by the Government, and as described in Paragraph A or B below.

- Lessor Provided Design Intent Drawings:

As part of the rental consideration, including the Tenant Improvement Allowance, the Lessor shall prepare and provide to the Government, for the Government’s approval, Design Intent Drawings detailing the Tenant Improvements to be made by the Lessor within the leased premises. The Government shall use best efforts to coordinate the provision of such information and details as required by the Lessor’s architect to complete such drawings in a timely manner. For purposes of this Lease, Design Intent Drawings, are defined as fully-dimensioned drawings of the leased space which include enough information to prepare construction drawings and shall consist of: 1) furniture locations, telephone and data outlet types and locations, electrical outlet locations, switch locations, ceiling grid height and light fixture locations, and cabinet/counter and shelving locations; 2) specifications necessary for calculation of electrical and HVAC loads; 3) all finish/color/signage selections, and 4.) security requirements. Design Intent Drawings shall be due from the Lessor within <insert # of business days> business days from the date of award.

OR

- Government Provided Design Intent Drawings:

The Government shall prepare and provide to the Lessor the Government’s approved Design Intent Drawings based upon the base building drawings provided by the Lessor as required in “PART V - GENERAL BUILDING REQUIREMENTS AND SPECIFICATIONS” of the submitted SFO. These Design Intent Drawings shall detail the Tenant Improvements to be made by the Lessor within the leased premises. Design Intent Drawings, for the purposes of this lease, are defined as fully-dimensioned drawings of the leased space which include enough information to prepare construction drawings and shall consist of: 1) furniture locations, telephone and data outlet types and locations; 2) specifications necessary for calculation of electrical and HVAC loads; 3) all finish/color/signage selections; and 4.) security requirements. Design Intent Drawings shall be due to the Lessor within <insert # of business days> business days from the date of award. If the Government provided Design Intent Drawings require additional design work after submittal to Lessor, then the Lessor will immediately complete that requirement, at Lessor’s cost, and submit said drawings back to the Government for review and approval, said review and approval shall be provided within <insert # of business days> business days from the date submitted by the Lessor.

REVIEW: The Government has the right to review, approve, and request modifications (if necessary) to the Lessor’s Design Intent Drawings at any time prior to the Lessor’s commencement of working/construction drawings. The Government’s review and approval of the drawings is limited to determining whether the drawings meet the specific requirements of the submitted SFO and this Lease. The Government shall perform all reviews of Design Intent Drawings within <insert # of business days> business days of receipt from Lessor. If the Government fails to provide the review within the requisite number of business days, the lease shall be modified to reflect a new occupancy date, which modification shall be at no cost to the Government. Should the Government disapprove the Lessor’s Design Intent Drawings, such disapproval, and the documented reasons, shall be provided in writing to the Lessor executed by the Real Estate Contracting Officer. Lessor shall have <insert # of business days> business days to cure all noted deficiencies in the Design Intent Drawings, and the revised Design Intent Drawings shall be resubmitted to the Real Estate Contracting Officer for review and approval. Upon approval of the Design Intent Drawings, a notice to proceed shall be transmitted to the Lessor, and the Lessor shall commence working/construction drawings for the space.

At the sole discretion of the Government, the Lessor may be required to submit a budget proposal, based on the Tenant Improvements and associated work as shown on the Design Intent Drawings. This budget proposal shall be completed within 10 business days from the date of the Government’s request. Delay of receipt of such proposal shall result in a Lessor delay and delay in the rent commencement after acceptance of lease premises.

  - – WORKING/CONSTRUCTION DRAWINGS (7/10)

The Lessor shall prepare, as part of the Tenant Improvement Allowance, final working/construction drawings for the improvements illustrated on the Government-approved Design Intent Drawings. The working/construction drawings shall include all mechanical, electrical, plumbing, fire safety, lighting, structural, and architectural improvements scheduled for inclusion into the leased premises. Working/construction drawings shall also be annotated with all applicable specifications. The resulting product shall reflect requirements which are substantially the same as that specified by the Government-approved Design Intent Drawings and shall incorporate neither extraneous additions nor deletions of Government requirements. The Lessor’s working/construction drawings shall be due to the Government within <insert # of business days> business days of the Government’s approval of the Design Intent Drawings. Working/construction drawings shall clearly identify 1) Tenant Improvements already in place and 2) the work to be done by the Lessor or others.

  - – REVIEW OF WORKING/CONSTRUCTION DOCUMENTS (10/12)

The Government shall have the right to review and request modifications to, the Lessor’s construction documents prior to the Lessor’s commencement of interior construction. The Government’s review of the construction documents is limited to determining the extent of the construction documents’ conformance to the specific requirements of the submitted SFO, lease attachments, and to the approved Design Intent Drawings. The Government shall perform all reviews of construction documents within <insert # of business days> business days from the date of receipt from the Lessor. If the Government is delayed in review of drawings, the lease shall be modified to reflect a new occupancy date. Should the Government require that modifications be made to the Lessor’s construction documents, the Government shall state such in writing to the Lessor, and the Lessor shall have <insert # of business days> business days to cure all noted defects before returning the construction documents to the Government for a subsequent review. Lessor shall obtain the necessary permits once the working/construction documents have been approved by the Real Estate Contracting Officer. Notwithstanding the Government’s review of the construction documents, the Lessor is solely responsible and liable for ensuring the technical accuracy of the construction documents.

  - – TENANT IMPROVEMENTS PRICE PROPOSAL BASED ON CONSTRUCTION DRAWINGS (10/12)

Within <insert # of business days> business days of Government review of the construction/working documents, the Lessor must submit the written price proposal along with cost and pricing data or the documentation of the competitive proposals and for any costs or credits to the Government. Any work shown on the construction documents that is building shell shall be clearly identified and priced as such. After negotiation and acceptance of the Tenant Improvements price, A NOTICE TO PROCEED SHALL BE TRANSMITTED TO THE LESSOR, and the Lessor shall commence construction of the Tenant Improvements. (See ‘Part I – Tenant Improvements and Tenant Improvement Allowance’ for more information). The Government reserves the right to disapprove the Lessor’s final tenant improvement cost prior to forwarding payment. Lessor shall provide copies of paid invoices to contractors and sub-contractors with whom the approved price proposal was developed. These paid invoices shall be submitted with the final invoice for payment due unless amortized within the rent.

    - – HIGH PERFORMANCE SUSTAINABLE BUILDING (HPSB) REQUIREMENTS (10/12)

For projects 5,000 sq. ft. and above, by the lease commencement date the Lessor must provide certification of compliance with the Guiding Principles for High Performance Sustainable Buildings (HPSB). By way of example, a completed checklist from the Energy Star Portfolio Manager which would indicate that the leased premises meet the Guiding Principles or requirements for a green label certification may be used as evidence of compliance.

  - – CONSTRUCTION OF TENANT IMPROVEMENTS (10/12)

- The Lessor shall construct all Tenant Improvements in accordance with 1) the Government reviewed working/construction drawings and 2) all terms and conditions of the submitted SFO and lease attachments. The Lessor shall complete Tenant Improvements within <insert # of business days> business days of receiving the notice to proceed from the Government. The Lessor shall furnish a detailed construction schedule (such as Critical Path Method) to the Government within 5 business days of issuance of the notice to proceed. Such schedule shall also indicate the dates available for the Government contractors to install telephone/data lines or equipment. The Government reserves the right to access any space within the building during the conduct of interior construction for the purposes of performing inspections or for installing Government-furnished equipment. The Government shall coordinate with the Lessor the activity of Government contractors in order to minimize conflicts with, and disruption to, other contractors on site. Access shall not be denied to authorize Government officials including, but not limited to, Government contractors, subcontractors, or consultants acting on behalf of the Government with regard to this project.

- Once the government has approved the construction/working drawings and the Lessor’s price proposal in accordance with the terms of this Attachment B, all changes to tenant improvements shall come within the scope of the “changes” clause set forth in paragraph 7K of the general clauses to this lease, and shall be processed accordingly.

  - – PROGRESS REPORTS (7/10)

After construction commencement, the Lessor shall submit to the Real Estate Contracting Officer, written progress reports at intervals of <insert # of business days> business days. Each report shall include information as to 1) percentage of the work completed by phase and trade; 2) a statement as to expected completion and occupancy date; 3) changes introduced into the work; and 4) general remarks on such items as material shortages, strikes, weather, etc. In addition, the Lessor shall conduct meetings every <insert # of weeks> week(s) to brief Government personnel and/or contractors regarding the progress of design and construction of the Government-demised area. The Lessor shall be responsible for taking and distributing minutes of these meetings, with shall be subject to review and approval by the Real Estate Contracting Officer. Such meetings shall be held at a location to be designated by the Government.

  - – CONSTRUCTION INSPECTIONS (10/12)

- Prior to the start of construction and after the approval of construction drawings by the Government, the Lessor and the Government shall arrange a pre-construction meeting. After construction has begun, construction inspections shall be made periodically by the Real Estate Contracting Officer and/or designated technical representatives to review compliance with the submitted SFO and Lease attachments and the final working drawings.

- Periodic reviews, witnessing of tests, and inspections by the Government are not to be interpreted as resulting in any approval of the Lessor's apparent progress toward meeting the Government's objectives but are intended to discover any information which the Real Estate Contracting Officer may be able to call to the Lessor's attention to prevent costly misdirection of effort. The Lessor shall respond in writing to the Real Estate Contracting Officer regarding the Government’s comments resulting from the subject reviews, tests, and inspections. The Lessor shall remain completely responsible for designing, constructing, operating, and maintaining the building in full accordance with the requirements of the submitted SFO and Lease attachments.

PART III - POST AWARD REQUIREMENTS

  - – AS-BUILT FLOOR PLANS AFTER OCCUPANCY (10/12)

The Lessor must follow the requirements in Attachment A, Section D16 for plans.

  - – MEASUREMENT OF SPACE (7/10)

The Lessor must follow the requirements in Attachment A, Section D for measurement of space.

  - – AIR BALANCE REPORT (10/12)

Lessor shall provide an Associated Air Balance Council (AABC) Certified Air Balance Report performed by a certified Mechanical Engineer based upon the approved Construction/Working Drawings. The Report shall cover typical air balance requirements for lease premises, and shall include all heating, ventilation, and air conditioning (HVAC) equipment, including (but not limited to) roof top and/or ground mounted units, trunk lines and ducting to the variable air volume (VAV) boxes, the VAV boxes, and ducting to and including the supply and return air grilles.

The results of the report shall comply with local codes and American Society of Heating, Refrigerating and Air Conditioning Engineers (ASHRAE) standards. If there is a conflict between the local codes and ASHRAE standards, the ASHRAE standards will govern and control.

  - – WALK-THROUGH AND ACCEPTANCE OF SPACE (10/12)

During the Walk-Through and Acceptance of Space, the Lessor shall provide the information described in 1.18, 1.19, and 1.20 above; and the Lessor will explain administrative/management procedures such as control of the thermostats,  janitorial hours, building opening and closing times, evening guard services, etc.

<insert # of business days> business days prior to the completion of interior construction, the Lessor shall issue written notice to the Government to inspect the space. The Government shall have <insert # of business days> business days to inspect and to either accept or reject the subject space. Substantially completed space shall be accepted by the Government subject to the completion of minor punch list items (see attached punch list). Space which is not substantially complete shall not be accepted by the Government. Should the Government reject the Lessor’s space as not substantially complete as defined herein, the Lessor shall immediately undertake remedial action and when such action is completed, shall issue to the Government a second notice to inspect.

  - – OCCUPANCY PERMIT (10/12)

The Lessor shall provide a valid Certificate of Occupancy, issued by the local jurisdiction, for the intended use of the Government and shall maintain and operate the building in conformance with current local codes and ordinances. The premises, all access to the premises, and building operations, shall be free of safety, health and fire hazards. If at any time after the execution of the lease, the premises are discovered to not be in compliance with any applicable current local code or ordinance, particularly as such local codes and ordinances pertain to fire, life safety, and health, the Lessor shall be responsible for bringing the premises into compliance with said codes or ordinances at no cost to the Government. If the local jurisdiction does not issue Certificates of Occupancy, the Lessor shall obtain the services of a licensed fire protection engineer to verify the offered space meets all applicable local codes and ordinances to ensure an acceptable level of safety is provided.

  - – RENT COMMENCEMENT (7/10)

The rent commencement date (for each increment) shall be the date that the leased premises are accepted in writing by the Government. Any rental paid by the Government prior to actual occupancy shall not include the cost for services and utilities. In any event, the Government shall not be required to accept space and commence rent prior to the original date as indicated in <insert name of document>.

  - – LEASE COMMENCEMENT (7/10)

The Government shall issue Supplemental Lease Agreement, to establish the lease commencement date after the acceptance of all space, if different from the date previously established in the lease. In any case, the rental commencement date shall not be prior to the commencement date of the lease.

  - – OTHER REQUIREMENTS (7/10)

The Lessor must follow all other requirements (i.e. Davis Bacon Act, Security, etc.) outlined in Standard Space Lease and Attachment A.

  - – REQUIRED INFORMATION POST AWARD: GREEN LABEL CERTIFICATION FOR SUSTAINABILITY VERIFICATION (10/12)

Following award of this Lease, the Lessor shall submit the information set forth herein to the Real Estate Contracting Officer within the designated time frames.

- Product Data Sheets for floor coverings, paints and wall coverings, ceiling materials, all adhesives, wood products, suite and interior doors, subdividing partitions, wall base, door hardware finishes, window coverings, millwork substrate and millwork finishes, lighting and lighting controls, and insulation to be used within the leased space. This information must be submitted NO LATER THAN the date of submission of the final Design Intent Drawings for the leased space, as outlined in paragraph 2.7 of this Attachment B.

- Upon request from the Real Estate Contracting Officer, the Lessor shall provide Material Safety Data Sheets (MSDS) or other appropriate documents for products listed in paragraph “Indoor Air Quality During Construction”.

- Any waiver required by the failure or inability of the Lessor to use materials from the CPG and RMAN lists of acceptable products are due within <insert # of business days> business days to the Real Estate Contracting Officer.

- Radon test results as may be required by the “Radon in Air” and “Radon in Water” as discussed in Attachment A.

- Construction Waste Management Plan:

Prior to issuance of the notice to proceed with construction, a proposed plan to recycle construction waste that follows industry standards MUST BE SUBMITTED BY THE LESSOR. The construction waste management plan shall at a minimum, include:

  - The Lessor’s Waste Management Diversion goal;

  - A statement of the relevant construction debris and materials to be diverted;

  - Lessor’s implementation protocols; and

  - The names and contact information of the parties responsible for implementing the plan.

The construction waste management plan shall quantify material diversion goals and maximize the materials to be recycled and/or salvaged, which shall not consist of less than 50 percent of the materials used in or obtained from construction, demolition, and packaging debris. The lessor must provide documentation of the actual percentage of material diverted from the applicable landfill. If the quantity of material to be diverted is small, the waste disposal method is determined to be extraordinarily complex, or the cost of such diversion and recycling efforts would be cost-prohibitive and, consequently, would represent a genuine hardship, the Government, upon written request of the Lessor and approval of the Real Estate Contracting Officer, may permit an alternative means of disposal.

- Building Recycling Service Plan:

A building recycling service plan with floor plans annotating recycling area(s) shall be submitted as part of Design Intent Drawings to be reflected on the Construction Drawing submission.

- The Lessor shall provide to the Real Estate Contracting Officer a signed statement explaining how all HVAC systems serving the leased space shall achieve the desired ventilation of the space during the flush-out period called for in Attachment A.

- Prior to the submission by the Lessor of the completed Design Intent Drawings, the Lessor shall submit to the Real Estate Contracting Officer a written commissioning plan submitted that includes:

- A schedule of systems commissioning dates (revised as needed during all construction phases of the project, subject to the review and approval of the Real Estate Contracting Officer in accordance with the “Changes” clause; and

- A description of how commissioning requirements shall be met and confirmed.

Lessor’s approval of this ATTACHMENT B ___________________    Date _________

The Government’s approval of this ATTACHMENT B _______________    Date _____