## Space Checklist
SPACE LEASE - FAA ACQUIRED PROJECT & FILE CHECKLIST
| AMS Links: | AMS Real Estate Policy - See Section 4.2
Real Estate Guidance
Real Estate Templates
Facility:
City/State:
Lease Number:
| Tab | Item | In File? | N/A
Organize Tabs in 6 part file folder
| 1 | REQUIREMENTS/PLANNING/BUSINESS CASE DEVELOPMENT
Initial Request
I |  | The acquisition process may start with an informal, written request or a zero dollar Procurement Request.
C |  | (RE Policy RE Policy 4.2.3.2 Request & 4.2.3.3. Requirements; RE Guidance 2.2.1 Request & 2.2.5 Advertising/Market Survey and Appraisal)
| * | Space Lease Project Checklist (Prepare new 6-part lease folder and insert this Project Checklist under Tab 17)
C |  | (RE Policy 4.2.3.13 Documentation)
| * | RETS *File under Data Records - Tab 15.
I |  | Enter New Project in RETS and place interim copy of RETS project screen in file to show assignment.
C |  | (RE Policy 4.2.3.9 Award)
Delineated Area Defined
I |  | RECO to work with LOB to define.
C |  | (RE Policy 4.2.3.3 Requirements & 4.2.3.5 Solicitation for Offers; RE Guidance 2.2.5 Advertising/Market Survey and Appraisal & 2.4.3)
Rural Development Act Checklist
I |  | Whenever possible the FAA is to give first priority to rural areas when locating new offices or other facilities where personnel are assigned. If a rural location is not selected the reason(s) should be explained. This does not apply to succeeding leases for existing locations.
C |  | (RE Policy 4.2.3.3.2.3 Rural Development Act Requirements; RE Guidance 2.4.3: Appendix C: Rural Development Act Guidance; RE Template 2.6.16 Rural Development Act {RDA} Checklist; DOT Order 4320.1A, Location of New Federal Offices and Other Facilities in Rural Areas)
Preliminary, Limited Market Survey
I |  | Gather preliminary market data for use by LOB, in Business Case preparation, and other estimates.
C |  | (RE Policy 4.2.3.3; RE Guidance 2.2.5 Advertising/Market Survey and Appraisal)
| * | Evaluation of Lease to Determine Accounting Treatment, Pre-Lease Review Based on preliminary market data. *File Pre-Lease Review document under Accounting Records, Tab 14. **If Capital lease, STOP, and seek advice from RE Policy Office!
I |  | It is FAA policy to avoid establishment of capital leases or lease purchases unless the requesting organization demonstrates they have complied with the requirements of OMB Circular A-11, Part 8, Appendix B "Scoring of Lease Purchases and Leases of Capital Assets".
C |  | (AMS Procurement Policy 3.8.5.2; RE Policy 4.2.3.9.1 Terms of Leases; RE Guidance 2.2.2 Requirements and Planning; RE Template 3.2.1 Lease Evaluation Form)
Business Case/Space Project Proposal for Administrative Space
I |  | Required for all administrative space, including new office construction, facility or office upgrade projects, lease expansions/contractions, succeeding leases, renewal options, and new lease locations. Must have approved Business Case before proceeding with full market survey & solicitation. (AMS 2.2.5)
I |  | Approval/Signature Thresholds: LOB Project and Budget Approval Real Estate Group Managers - Annual rent $0 - $100K Logistics Service Area Managers - Annual rent over $100K - $350K ALO-1 - Annual rent over $350K up to $1M ARC-1 - Annual rent over $1M CFO Approval required where total contract value, including options is $10M or more OMB Approval: Certain leases (e.g. Capital Leases, Prospectus leases; etc.) require OMB review. See OMB Circular A-11, Appendix B for the full list. Prospectus/Congressional Approva): GSA has authority to index the threshold and change it each year. As of FY13: Net annual rent, excluding services & utilities, exceeds $2.79 Million Alterations in leased buildings exceed $1.395 M
C |  | (RE Policy 4.2.3.3.2.1 Administrative Space Standards; RE Guidance 2.2.5 Advertising/Market Survey and Appraisal; 2.4.1: Appendix A: Administrative Space Guidance; FAA Order 4665.4. CFO: AMS Procurement Policy 3.2.1.4.2 Chief Financial Officer Approval; RE Guidance 2.4.1.2 Chief Financial Officer Review of GSA Space Request over $10M & 7.6 Real Property Acquisition. OMB: AMS RE Policy 4.2.3.9.1 Terms of Leases; RE Guidance 3.1.5: Capitalization. Federal Management Regulations Part 102-73 & 40 U.S.C. 606 **To look up current threshold amount, go to GSA.GOV and type in 'Prospectus Threshold' ) (Space Project Proposal reference: Fiscal Year 2014 Financial Guidance from Mark House, FAA Chief Financial Officer, January 24, 2014; Delegation of Approval Authority for Administrative Space Leases from Ray Towles, ARC-1, July 9, 2014.)
Requirements from Customer
I |  | In sufficient detail to develop an SFO, which may include Space Requirements Questionnaire 2.6.14.
C |  | (RE Policy 4.2.3.4 Procurement Method & 4.2.3.3 Requirements & 4.2.3.3.2.1 Administrative Space Order 4665.4; RE Guidance 2.2.2 Requirements and Planning & RE Guidance 2.4.1 Appendix A: Administrative Space Guidance; RE Template 2.6.14 Space Requirements Questionnaire)
| * | Security Facility Requirements for SFO/Sample Lease *File under Security, Tab 11.
I |  | RECO to schedule meeting between end user and SSE to determine end user requirements. SSE to provide baseline Facility Security protective measures for RECO to include in SFO or sample lease.
C |  | (RE Policy 4.2.3.3.2.4 Security Requirements; RE Guidance 2.4.7 Appendix G: Security; FAA Order 1600.69B FAA Facility Security Management Program)
| * | Initial Procurement Request *File under Accounting -Tab 14.
I |  | The acquisition process may start with an information request. The initial P.R. can be for any amount, including zero dollars. However, prior to issuing an SFO or other formal request for information or quotes, the RECO must confirm that certified funds for the current fiscal year (if required) are available for obligation. AMS Procurement Toolbox - T3.2.1 - Procurement Planning, Procurement Request 13:Real Property contains information on what should be in the written request/P.R. package.
C |  | (RE Policy RE Policy 4.2.3.2 Request & 4.2.3.3. Requirements; RE Guidance 2.2.1 Request; RE Guidance 2.2.5 Advertising/Market Survey and Appraisal)
Other: List other significant documents filed in this section
| 2 | PRE-SOLICITATION/PROCUREMENT METHOD
Firm Term (Funding) Statement from LOB
I |  | Written statement from LOB acknowledging funding commitment for non-cancellable (firm term) portion of requested lease if firm term of lease exceeds current fiscal year
C |  | (RE Guidance 2.4.4: Appendix D: Lease Terms)
Firm Term Approval from ALO-200
I |  | Required for space lease with firm term greater than 10 years.
C |  | (RE Guidance 2.4.4: Appendix D: Lease Terms)
Pre-Solicitation Coordination (Legal) Notify Legal of any new request/PR for real estate action. Place copy of notification in file. or Waiver from Legal Coordination (in writing - signed by Legal Counsel)
C |  | (RE Policy 4.2.3.1 Legal Coordination of Real Property Actions; RE Guidance 7: Legal Coordination & 7.5 Coordination between the Service Organization and Agency Counsel; AMS 1.2.13 Legal Coordination)
Competitive Determination (Applies to succeeding space leases.)
I |  | Includes: Cost Estimate to Relocate, Cost Analysis & Justification. *Required for all succeeding leases that will not be competed but meets definition for “competitive determination”. Legal review of competitive determination not required.
C |  | (RE Policy 4.2.3.1 Legal Coordination of Real Property Actions; RE Guidance 7: Legal Coordination & 7.5 Coordination between the Service Organization and Agency Counsel; AMS 1.2.13 Legal Coordination)
Single Source (Noncompetitive) Justification Form
I |  | Required for new leases that will not be competed and cannot support a “Competitive Determination”. Exception: If exercising an option to renew or a succeeding lease at the same location and either establishing a new lease term and a new rental price, or both, and NO OTHER MATERIEL provisions have been changed, the RECO is NOT required to prepare single source justification (must prepare a competitive determination).
C |  | (RE Policy 4.2.3.1 Legal Coordination of Real Property Actions; RE Guidance 7: Legal Coordination; AMS 1.2.13 Legal Coordination; Template 7.9.2 Single Source Justification Template )
Legal Review for Single Source (Noncompetitive) Acquisitions - Over $10K
I |  | Required if lease will not be competed (single source), cannot support a 'competitive determination' and total contract value, including all possible options, exceeds $10K.
C |  | (RE Policy 4.2.3.1 Legal Coordination of Real Property Actions & 4.3.3.5 Solicitation for Offers; RE Guidance 7: Legal Coordination & 2.2.3 Procurement Method; RE Template 7.9.1 Legal Review and Concurrence Form)
Certificate of Nondisclosure
I |  | Source selection information and proceedings shall not be discussed outside the service organization. The Source Selection Officer (SSO) shall determine the extent to which source selection information is disclosed and shall execute a Certificate of Nondisclosure as appropriate.
C |  | (RE Policy, 4.2.3.14.1 , Disclosure of Information; Use Procurement Form - Agreement Regarding Non-Disclosure of Information
Other: List other significant documents filed in this section
| 3 | MARKET SURVEY/SOLICITATION
| * | Davis-Bacon: Obtain Wage Rate Determinations from DOL *File all DB documents under DAVIS BACON, Tab 8.
I |  | Required in solicitations and leases where new construction or alteration of space exceeds $2,000. If applicable, review Tab 8 for DB requirements. RECO to obtain wage determination information from DOL and incorporate into SFO or include language that SFO will be amended to incorporate any wage determinations prior to award.
C |  | (RE Policy 4.2.3.10 Alterations and Improvements; RE Guidance 2.4.13:Appendix M: Labor Standards/Davis Bacon; Procurement Toolbox Guidance: T3.6.2-6: Procedures for Construction Contract; 2.6.9.1 Small Space Lease Instructions and Prescriptions)
Obtain Lease # from PRISM for use on SFO/Lease (do not award in PRISM until lease is signed)
Solicitation For Offers/Proposed Sample Lease
I |  | If RECO determines SFO will be used, include full copy of SFO, including all attachments, in file. If only a proposed lease is used to solicit offer(s), include copy of proposed lease. For space under 3,000 sq. ft., a modified version of an SFO is acceptable for the RECO to use.
C |  | (RE Policy 4.2.3.5 Solicitation for Offers; RE Guidance 2.2.6 Request for Offers/Solicitation for Offers; RE Template 2.6.12 Solicitation for Offers)
Airport Traffic Control Tower Operation Agreement
I |  | If facility is for an Airport Traffic Control Tower, RECO to attach Operation Agreement to Lease.
C |  | RE Template 2.6.30.1 Operation Agreement for airport Traffic Control Tower)
Advertisement (Copy of Ad)
I |  | If RECO determines that advertising is warranted, use publicizing method most likely to result in receipt of offers appropriate to satisfy the specific requirement.
C |  | (RE Guidance 2.2.5 Advertising/Market Survey and Appraisal)
Conduct Market Survey/Market Survey Forms (Full or Limited)
I |  | Full Market Survey must be conducted for all new and succeeding space leases. Limited Market Survey – As a minimum, required if a full market survey is not performed. RECO can use a limited market survey for small space leases (3,000 sf or less) or when exercising a renewal option previously negotiated. Market Survey Form is required for each location surveyed, whether a full survey or a limited survey is conducted.
C |  | (RE Guidance 2.2.5 Advertising/Market Survey and Appraisal; RE Template 2.6.10 Space Market Survey Form)
Misc. Market Information (Flyers, Brochures, BOMA information, etc.)
Formal Appraisal
I |  | As deemed necessary by RECO or if information cannot be obtained through a market survey.
C |  | (RE Guidance 2.2.8 Evaluation of Offers)
Cost Estimates for Alterations and/or Improvements, including initial Tenant Improvements
I |  | In making the determination of whether a lessor’s proposed costs to make alterations and improvements to a leased facility are reasonable, the RECO should use a 1.) formal appraisal, 2.) construction data, 3.) cost to build publications, and/or 4.) an independent government cost estimate. For large leases, RECO may use engineers/architects from Design and Construction, ALO-100C, to verify cost estimates.
C |  | (RE Policy 4.2.3.10: Alterations and Improvements; RE Guidance 2.3.2 Alterations and Improvements)
| * | Reasonable/Competitive Range for Rents/Fair Market Value Established
I |  | Based on Market Surveys, Market Information or Appraisal. (*This information must be included in the final Negotiator’s Report, under Tab 5.)
C |  | (RE Guidance 2.2.5 Advertising/Market Survey and Appraisal)
SFO/Proposed Sample Lease Distribution List - with LOB Concurrence
C |  | (RE Guidance 2.2.5 Advertising/Market Survey and Appraisal)
Letter(s) or email(s) distributing SFO and/or Proposed Contract to potential Offeror(s)
C |  | (RE Guidance 2.2.6 Request for Offers/Solicitation for Offers)
Other: List other significant documents filed in this section
| 4 | NEGOTIATION
| * | Initial Review of Proposal To Lease/Offer(s) Received
I |  | Fill out Offer Review - Space Form (Template 2.66.1) for each offer received, including offer from an incumbent Lessor. Include any notes, spreadsheet, or other documentation based on the initial evaluation, noting any deficiencies that must be addressed with Offeror(s). File any unsuccessful offers and supporting documentation under Tab 4. Once an offer is selected for award, file the completed Offer Review form long with the final offer and all completed supporting documentation under Tab 6 - Pre-Award Approvals or Tab 17 - Lease.
C |  | (AMS RE Policy 4.2.3.6.1 Negotiation; RE Template 2.6.6.1 Offer Documentation Review (Space)
| * | Davis Bacon – Wage Rate Determinations from DOL (Updates) *File all DB documents under DAVIS BACON, Tab 8.
I |  | RECO to check for any updates prior to award and amend SFO as necessary before award. (Award of Contract Without Required Wage Determination: If DOL discovers after award that the wrong wage determination or rate schedule was specified, the CO will modify the contract to incorporate the corrected wage determination (retroactive to the date of award), or terminate the contract. If appropriate, the CO should equitably adjust the contract price. )
C |  | (Procurement Toolbox: Procurement Guidance:T3.6.2 - Labor Laws, paragraph 6 Procedures for Construction Contracts)
LOB Concurrence - Deviations from Requirements
I |  | Written concurrence required from LOB for any clauses that deviate from customer requirements or minimum agency standards that may impose obligations on the LOB - financial or otherwise. E.g. early termination penalty, restoration, seismic exception, specific tenant rules, etc.
C |  | (RE Guidance 1.2 Land Clause Matrix; 2.4.8 Appendix H Seismic)
Chief of the Contracting Office Concurrence - Deviation from Mandatory Clauses
I |  | LSAM to approve justification for deviating from any of the mandatory clauses. This is in addition to Legal approval. AMS clauses and provisions used in screening information requests and contracts must be consistent with the procurement guidance and prescriptions in the FAST Procurement Toolbox, unless there is an approved rational basis for adopting a different approach. The Chief Counsel’s office and Chief of the Contracting Office must approve in advance each such rational basis determination regarding the use or tailoring of a mandatory clause or provision.
C |  | (AMS Procurement Policy 3.13.2.1)
Legal Concurrence for Non-standard Clauses
I |  | Includes any deleted or revised mandatory clauses or any added clauses. Obtain prior to ending negotiations & ensure changes do not offer unfair advantage to one party over another. RECO must place a copy of ALO-200 and AGC-500 approval in the file for any changes approved by local Legal Counsel that are meant to be used as the local standard.
C |  | (RE Policy 4.2.3.1 Legal Coordination & 4.2.3.6.2 Communication & 4.2.3.3.1 Succeeding/Renewal Leases; RE Guidance Section 7 Legal Coordination & 2.2.10 Award)
Notes/Correspondence (pre-award) - Include any written notes, conversations, meetings, etc. that capture negotiations conducted with Offerors. These will form the basis of the final Negotiator's Report.
Other: List other significant documents filed in this section
| 5 | EVALUATION
Evaluation of Offers
I |  | The evaluation criteria should be in writing and the lease file should indicate how the criteria was used.
C |  | (RE Guidance 2.2.8 Evaluation of Offers)
Present Value Analysis of Offers
I |  | Not required if all offers received are level over the entire term. The length of the lease determines whether actual or discounted dollars are used. Programs to evaluate discounted dollars are available.
C |  | (RE Guidance 2.2.8 Evaluation of Offers)
Negotiators Report
C |  | (RE Policy 4.2.3.6.1 Negotiation; RE Template 2.6.18 Negotiators Report & Template 2.6.18.1 Authorities Reference)
| * | Prepare Draft Lease for Selected offer *Discard extraneous drafts once final lease is awarded.
Other: List other significant documents filed in this section
| 6 | PRE-AWARD APPROVALS (Apparent successful Offeror)
Final Review/Document Check of Apparent Successful Offer
I |  | RECO to conduct final review for completeness of the offer using the Offer Review - Space Form 2.6.6.2. For the successful Offeror, file the Offer Review - Space Form 2.6.6.1 , along with any modifications and supporting documentation, e.g. ABASS, Seismic, Safety form, etc. under Tab 6; except for Security Review of proposed final location (File under Security, Tab 11); and Ownership Verification and Authorization to Sign on behalf of Owner (File under Tab 17).
C |  | (AMS RE Policy 4.2.3.6.1 Negotiation; RE Template 2.6.6.1 Offer Documentation Review (Space)
EDDA Documentation 0 EDDA Memo (Appendix B) and/or Waiver (Appendix C) or 0 EDDA Report Phase I and signed Technical Review Letter and, if applicable, Phase II & Remediation Plan or 0 For succeeding leases with no changes in size, if LOB fails to provide EDDA documentation, RECO to place statement in Negotiator Report showing evidence of attempt to secure
I |  | The LOB is responsible for providing the RECO with EDDA documentation that satisfies FAA Order 1050.19B. For new acquisitions (new locations or increasing/decreasing the size of the existing location), the RECO is not to finalize the real estate transaction until the appropriate documentation (EDDA report, memorandum and/or waiver) is approved by the LOB. For succeeding leases in the same location where there are no changes in the area under lease (either increasing or decreasing in size), if the appropriate documentation (EDDA report, memorandum and/or waiver) is not provided either by the LOB or upon request by the RECO, the RECO can proceed with the succeeding lease award but must document the lease file showing evidence of the attempt to secure the documentation from the LOB.
C |  | (AMS Procurement Guidance T3.2.1 Real Property; AMS RE Policy 4.2.3.3.2.8 Environmental/Sustainability/Energy Considerations; AMS RE Guidance 2.4.16 Environmental/Sustainability/Energy; FAA Order 1050.19B)
Notify LOB on Recommended Award
C |  | (RE Guidance 2.2.8 Evaluation of Offers)
| * | Final Procurement Request (P.R.) *File P.R. under Accounting Records, Tab 14.
I |  | Must obtain prior to actual award (RECO signing of lease).
I |  | $0 Leases – obtain $0 PR;
I |  | Cost leases – obtain fully funded PR or if lease is to be awarded (signed) prior to the start of the fiscal year in which the rent starts, obtain PR, subject to availability of funds.
C |  | (RE Policy RE Policy 4.2.3.2 Request & 4.2.3.3. Requirements; RE Policy 4.2.3.2 Request; RE Guidance 2.2.1 Request) *PRISM - Real Estate Guidance: https://employees.faa.gov/org/staffoffices/aba/prism/training/
| * | Evaluation of Lease to Determine Accounting Treatment, Final Review (based on actual award data) *File Final Review document under Accounting Records, Tab 14.
I |  | Must be signed by RECO & Accounting. If Capital lease, STOP, and seek advice from RE Policy Office!
C |  | (RE Policy 4.2.3.9.1 Term of Lease; RE Guidance 2.2.2 Requirements and Planning)
Legal Review & Concurrence - Over $100K
I |  | Review of proposed lease and lease file. Required for all real property acquisitions (new, succeeding, options to renew, and lease modifications) over $100K total contract value.
C |  | (RE Policy 4.2.3.1 Legal Coordination of Real Property Actions; RE Guidance Section 7: Legal Coordination; RE Template 7.9.1 Legal Review and Concurrence Form)
Contract Review signed by QA Personnel
I |  | RECO to fill out appropriate Lease Clause Checklist. RECO to submit lease, filled out lease clause checklist and Contract Review Form to designated QA reviewer before award. All space/structure leases require QA review except unoccupied leases below $100,000 annual rent. See ISO Work Instructions for detailed information.
C |  | (RE Guidance 2.2.9 Lease Review Process; RE Template 3.2.4 Contract Review Form)
| * | Personnel Security Information *File security requirements under Security, Tab 11.
I |  | RECO to obtain completed FAA Form 1600-77 from LOB and/or SSE for every individual employed/hired by the Lessor that will perform work or provide services in the leased space. In addition, if any personnel are aliens or foreign nationals, additional requirements apply in accordance with FAA Order 1600.72A, chapter 5, paragraph 7 & 8. RECO to retain all original approved 1600-77 forms in real estate file.
I |  | RECO to send instructions and the following forms to the Lessor for every non-exempt person requiring access to Government leased premises: - FD-258, FBI Fingerprint Card - SF 85P, Questionnaire for Public Trust Positions as designated by the FAA Form 1600-77 - DOT Form 1681, Card/Credential Application, needed to obtain PIV card. - Form I-9, Employment Eligibility Verification Lessor to return completed forms to SSE or Trusted Agent within 5 days, and not to exceed a maximum of 30 days after lease award.
C |  | (RE Policy 4.2.3.3.2.4 Security; RE Guidance 2.4.7 Appendix G: Security; FAA Order 1600.72A, Contractor and Industrial Security Program)
Other: List other significant documents filed in this section
| 7 | AWARD
Award Letter to Apparent Successful Offeror
I |  | Enclose at least 2 copies of lease for final (original ink) signature. Retain a file copy of actual lease sent for signature.
C |  | (RE Guidance 2.2.10 Award)
| * | Contracting Officer to Sign Lease *File signed lease under Tab 17.
I |  | Ensure no changes were made to returned lease. *Ensure CO’s warrant type & amount is sufficient to cover total potential value of the lease, including any options for renewal or lump sum payments.
C |  | (RE Policy 4.2.2.1 Contracting Authority; RE Guidance 2.2.10 Award)
| * | Award Purchase Order in PRISM *File PO document under Accounting Records, Tab 14.
I |  | If cost lease, initiate payment process to ensure prompt payment. Ensure copy of lease is sent to Accounting, along with payment schedule.
C |  | (*PRISM - Real Estate Guidance: https://employees.faa.gov/org/staffoffices/aba/prism/training/)
Award Letter to Lessor & LOB
I |  | Letter to Lessor conveying fully signed lease with a copy to Occupant Manager and Head of Regional/Service Area LOB Manager or POC.
C |  | (RE Template 2.6.12 – Solicitation for Offers)
Letter to Unsuccessful Offerors
I |  | Unsuccessful Offerors will be notified in writing by the RECO after lease award.
C |  | (RE Template 2.6.12 – Solicitation for Offers, paragraph 1.8 Award)
Award Protest Documentation
C |  | (Procurement Toolbox - AMS Policy Section 3.9 Resolution of Protests and Contract Disputes)
Other: List other significant documents filed in this section
| 8 | DAVIS BACON
Required in solicitations and leases where new construction or alteration of space exceeds $2,000. Attach and use the alternate expanded Build out and Davis Bacon checklist.
| 9 | BUILD-OUT
Required for all projects where new construction or alterations will be made to the space leased. File all correspondence, decisions, and information on initial build out or alterations of the space in this section of the lease file. Attach and use the expanded Build out and Davis Bacon checklist.
| 10 | INSPECTION & ACCEPTANCE
High Performance Sustainable Building Requirement - Completed checklist from Energy Star Portfolio Manager (ESPM) or - LEED Silver (or better) certification by a LEED Accredited Professional
I |  | For new leases or succeeding leases of 5,000 sq. ft. and above, by the lease commencement date, the Lessor must provide certification of compliance with HPSB. Certification of compliance must be provided in the form of either: a completed checklist from Energy Star Portfolio Manager (ESPM) that indicates that the leased premises meet the Guiding Principles, or LEED (Silver or better) certification by a LEED Accredited Professional.
C |  | (RE Guidance 2.4 Appendices, Environmental/Sustainability/Energy & 2.4.16 HPSB Appendix; RE Template 2.6.8 – Standard Space Lease, High Performance sutainable Building (HPSB) Requirements & 2.6.8.1 Standard Space Lease Instructions and Prescriptions )
ABAAS Compliance Inspection
I |  | If the Lessor has certified that space will be compliant by a certain date, the RECO must ensure space is compliant through inspection and certification by the FAA facility manager, or designee, or a site visit. See AMS for further remedies if Lessor fails to bring into compliance.
C |  | (RE Guidance 2.4.9 Appendix I: Accessibility)
Walk-Through and Acceptance of Space (Including final measurement of space.)
I |  | Lessor to issue written notice to RECO to inspect space. Condition report documented and signed by RECO and Lessor. If any minor items need to be addressed, develop punch list and follow up with Lessor on progress until complete. Substantial items that would impact FAA use/or occupancy must be corrected before acceptance.
C |  | (RE Policy 4.2.3.11 Inspection and Acceptance; RE Guidance 2.3.1 Inspection and Acceptance; RE Template 2.6.8 Standard Space Lease Walk Through and Acceptance of Space Clause & RE Template 2.6.8.1 Standard Space Lease Instructions and Prescriptions)
Occupancy Permit (aka Certificate of Occupancy)
I |  | Required for newly occupied space only. If local authority does not issue occupancy permits, RECO may accept the FAA Safety & Environmental Certification Checklist signed by the Lessor in lieu of occupancy permit.
C |  | (RE Guidance 2.3.1 Inspection and Acceptance; RE Template 2.6.8 Standard Space Lease & 2.6.9 Small Space Lease, Occupancy Permit clause & RE Template 2.6.8.1 Standard Space Lease Instructions and Prescription)
Final “As-Built” Drawings
I |  | If the As-Built Floor Plans After Occupancy (standard space lease) clause or the Floor Plans After Occupancy (small space lease) clause is included in the lease, the Lessor must submit a final set of hard copy as-built plans and reproducible floor plans in l/8" scale as required by the lease terms.
C |  | (RE Template 2.6.8 Standard Space Lease, As-Built After Occupancy clause & RE Template 2.6.8.1 Standard Space Lease Instructions and Prescription)
Meter Information for Utilities Not Provided by Lessor
I |  | If lease contains Utilities Not Provided By the Lessor clause, the Lessor will provide separate meters for utilities to be paid directly by FAA. When FAA is to pay for utilities, the Lessor will furnish the Real Estate Contracting Officer, prior to occupancy by the FAA, written verification of the meter numbers and certification that these meters will measure FAA usage only. If the cost of utilities for heating, ventilation, and air conditioning (HVAC) is not included as part of the rental considerations, an automatic control system will be provided to assure compliance with heating and air conditioning provisions included in the lease.
C |  | (RE Template 2.6.8 Standard Space Lease or 2.6.9 Small Space Lease, Utiliies Not Provided by the Lessor clause & RE Template 2.6.8.1 Standard Space Lease Instructions and Prescription)
| * | Final Reconciliation of Tenant Improvement Allowance – SLA *File SLA under Tab 17 - Lease/Lease Mod
I |  | If the lease contains tenant improvement allowance clauses, then RECO to complete a Lease Modification/Supplemental Lease Agreement establishing final tenant improvement allowance and any changes needed to the terms of the lease if the TI's are over or under the allowance.
C |  | (RE Guidance 2.4.11 Appendix K: Supplemental Lease Agreement)
| * | Rent Commencement/Lease Commencement Dates – SLA *File SLA under Lease/Lease Mod, Tab 17.
I |  | Lease Modification/Supplemental Lease Agreement establishing rent commencement date and/or lease commencement date – if different than dates established in the lease -- & any changes in square footage and associated clauses based on acceptance of the space.
C |  | (RE Guidance, 2.3.1: Inspection and Acceptance; )
Other: List other significant documents filed in this section
| 11 | SECURITY (Facility & Personnel)
File correspondence, clearances, inspections, waivers, and forms relating to all Security Requirements for the facility in this section.
Delegation of Contractor Security Program
I |  | The RECO should, whenever possible, delegate day to day management of the contractor security program at a leased facility to a responsible on-site representative (Contracting Officer Representative).
C |  | (RE Policy 4.2.3.3.2.4 Security; RE Guidance 2.4.7 Appendix G: Security)
Quarterly/bi-annual report of contractors accessing FAA premises
I |  | Lessor to provide Quarterly/bi-annual reports to the RECO and Servicing Security Element as required on or before the 5th business day following each reporting period. These listings must include a complete alphabetical listing of current employees working on the contract, and a separate list of terminated employees.
C |  | (RE Guidance 2.4.7 Appendix G: Security)
Personnel Security Information - Changes (On-Going)
I |  | The Lessor has an ongoing requirement to advise the RECO, or the designated Government representative, of changes to the Lessor/Contractor List. RECO to coordinate with Lessor on any changes to personnel requiring new Security Clearances.
C |  | (RE Policy 4.2.3.3.2.4 Security; RE Guidance 2.4.7 Appendix G: Security)
Other: List other significant documents filed in this section
| 12 | LEASE ADMINISTRATION
Contracting Officer Representative (COR) Documentation (if designated by RECO)
I |  | - Memorandum(s) of Delegation to COR (Template 2.6.23)
I |  | - Letter to Lessor for each delegation (Template 2.6.23.1)
I |  | - Proof of COR training
I |  | - Proof of Annual Validation of COR training
I |  | - Revocation of Delegation (if removing/replacing COR)
C |  | (RE Guidance 2.4.12 Appendix L: Contracting Officer Representative & 5.2.6.1 & 5.2.6.2 Contracting Officer Representative; RE Template: 2.6.23 Contracting Officer's Representative (COR) Designation Memorandum & 2.6.23.1 Contracting Officer's Representative Transmittal Letter)
Periodic Services Provided By Lessor
I |  | Applies to leases where janitorial services are provided by Lessor. Within 60 days after occupancy by FAA, the Lessor shall provide to the RECO a detailed written schedule of all periodic services and maintenance to be performed OTHER THAN daily, weekly, or monthly.
C |  | (RE Template 2.6.8 Standard Space Lease, Janitorial Services clause)
Correspondence - lease & contract administration (after occupancy) Internal & external letters, notes, memos, periodic lease review/inspection of facility, lease enforcement actions – file chronologically.
Other: List other significant documents filed in this section
| 13 | CLAIMS and DISPUTES (After award)
Claim or Dispute
Correspondence (all) regarding dispute or claim
Findings and Decisions of CO
Appeals from decisions
Final Resolution
Other: List other significant documents filed in this section
| 14 | ACCOUNTING RECORDS
PRISM (PRs, POs), DELPHI, Evaluation of Lease to Determine Accounting Treatment, etc. **Note: Once forms, which contain TIN/SSI or other Privacy Act Information are submitted to Accounting for final processing, copies of these documents are not to be kept in the lease folder.
Non-SAM Exemption
I |  | RECO to document rationale for granting exception to Lessor from registering in the System for Award Management (SAM). Justification must be kept in contract file.
C |  | (AMS Procurement Guidance T3.3.1.A-4, System for Award Management; RE Guidance 3.1.4.1 System for Award Management)
Vendor/Misc. Payment Information Form – Signed by Vendor **See note above.
I |  | To be used only for those vendors that are exempted from SAM.
C |  | (RE Template 3.2.2 Vendor/Miscellaneous Payment Information Form)
EFT Waiver Request Form
I |  | Must be signed by RECO and approved by Accounting if Lessor is granted exemption from payment via Electronic Funds Transfer.
C |  | (AMS Procurement Toolbox Guidance T.3.3.1.A-7 Electronic Fund Transfer; RE Guidance 3.1.4.2 Electronic Fund Transfer {EFT}; RE Template 3.2.3 Electronic Funds Transfer {EFT} Waiver Request Form)
DELPHI Vendor Entry Worksheet **See note above.
I |  | Provide to Accounting to set up a new Lessor in DELPHI.
C |  | (https://employees.faa.gov/org/staffoffices/aba/prism/training/resources/)
Follow on P.R.s (e.g. changes to cost, subsequent fiscal year funding, etc.). Latest PR filed on top.
Follow on Evaluation of Lease to Determine Accounting Treatment (e.g. changes to lease term, increased square footage, etc.). Signed by Accounting. Latest Determination filed on top.
Payment History/Research/Payment Resolutions (after award)
Obligation for Holdover/Expired Lease
I |  | If FAA continues occupancy after the ending date of the lease and the RECO has not negotiated: 1) a new succeeding lease, 2) signed a new lease extension with the Lessor to continue the lease, or 3) exercised a holdover provision or renewal option in the lease; The RECO must take action, each fiscal year, to coordinate with the LOB budget office and Accounting to ensure funds are set aside for anticipated rents that represent valid UNPAID obligations of the agency due to the inability to secure a valid contract.
C |  | (RE Policy 4.2.3.3.1.2 Emergency Reservation of Expiring Funds for Continued FAA Occupancy; RE Guidance 2.4.1 Holdover Tenancy)
At Contract End - Stop payment instruction to Accounting, as necessary.
Correspondence -- Payment Issues. (Any correspondence with Accounting and/or Lessor over payment issues.)
Other: List other significant documents filed in this section
| 15 | DATA RECORDS
*File all REMS, RETS, and Contact Information under this tab.
Contact List (Lessor, property management company, etc.) Keep at top of this tab for ready reference.
REMS (initial entry & any changes)
I |  | Enter required REMS data & scan copy of lease into REMS, including any mods. Place printed copy of "Lease Information" screen shot in file, initialed by REMS entry person.
C |  | (RE Policy 4.2.3.13.2 REMS)
RETS
I |  | Complete Project in Real Estate Tracking System (RETS). Print out project screen and all notes. Discard any duplicate or interim RETS print outs.
Other: List other significant DATA documents filed in this section
| 16 | HISTORICAL
Past Leases
I |  | Copy of all past leases, including all modifications. Remember to retain the original lease with the original project folder.
Other: List other significant documents filed in this section
| 17 | LEASE/LEASE MODS AND OWNERSHIP INFORMATION
Evidence of Ownership for successful Offeror & any subsequent ownership changes
C |  | (RE Template 2.6.12 Solicitation for Offers, Evidence of Capability to Perform)
Authorization to sign on behalf of owner, if negotiating with other than owner and any subsequent changes. (e.g. Corporate Certificate, Limited Liability Company Certificate, Board of Directors, Power of Attorney, etc.) Successful offeror only.
I |  | Review and confirm authority of Offeror(s) to sign on behalf of owner during the Initial & Final review of offers. Authority information shall be kept with the offers; however, the information for the successful offer shall be filed under this tab, 17.
C |  | (RE Template 2.6.1 LLC Certificate; RE Template 2.6.12 Solicitation for Offers)
Fully executed lease (original ink signature, signed by all parties)
Modifications/Supplemental Lease Agreements (File on top of base lease & Tab 17 checklist.)
I |  | Separate each mod by a sub-tab, to be consecutively numbered by lease mod #. If applicable, use separate lease mod checklist for each mod action and file on top of the mod it supports.
C |  | (RE Guidance Appendix K: Supplemental Lease Agreement)
Legal Review for Lease Modifications over $100K. (File with Lease Mod)
C |  | (RE Policy 4.2.3.1 Legal Coordination of Real Property Actions; RE Guidance Section 7: Legal Coordination; RE Template 7.9.1 Legal Review and Concurrence Form)
Signed Space Lease Project & File Checklist (File Checklist on top of base lease.) 'Check One: ____ Checklist Review is not required for this action ____ Checklist Review is required by AMS/ISO 9001 (Attach file review to checklist.) ____ Checklist Review is required based on Real Estate Group Manager’s discretion (Attach file review to checklist.) Project Checklist prepared by: ______________________________________________________ Date:___________ Signature of Preparer if different than RE Contracting Officer _____________________________________________________ Date:___________ Real Estate Contracting Officer Signature
I |  | See ISO 9001 Work Instructions to determine if a secondary review is required by AMS and check with the Service Area Quality Assurance person to determine if the Service Area Real Estate Group Manager requires additional reviews. The secondary review is not intended to replace the judgment exercised by the contracting officer.
C |  | (RE Guidance 2.2.9 Lease File Process; RE Template 2.6.20 Space Lease File Checklist)
I |  | 6-PART FOLDER LABEL INFORMATION (Minimum Information required on folder label. Additional information can be added at option of Service Area.)
I |  | City State File # ___ of ___ 'Facility Type Contract #
COMPRESS
EXPAND