## Estimated Lead Times
Estimated Acquisition Lead-Time |  |  |  |  | 2014-07-01
Note: The timeframes in this chart are estimated and purely for planning purposes only. As each FAA acquisition is unique and independent, the lead-time chart in no way obligates contracting offices to deliver in the timeframes below.
Action | Negotiated Competitive | Two-Step/ Multiple SIRs | Single Source (1) | SEDB/8(a) Competitive | Within Scope Changes
Complete PR Package Received | Start | Start | Start | Start | Start
OSBD Acceptance | 1 to 5 | 1 to 5 | 1 to 5 | 1 to 5 | 0
Market Analysis | 5 to 30 | 5 to 30 | 5 to 30 | 5 to 30 | 5 to 15
Announcement/Synopsis | 10 to 30 | 10 to 30 | 10 to 30 | 10 to 30 | 0
CO Review Requirements/Draft SIR | 5 to 10 | 5 to 10 | 5 to 10 | 5 to 10 | 1 to 10
SIR Review (Mgmt, Legal, etc) | 10 to 15 | 15 to 20 | 10 to 15 | 10 to 15 | 10 to 15
SIR | 30 | 60 | 10 to 30 | 10 to 30 | 0
Proposal/Quote/Technical Evaluation | 5 to 15 | 10 to 30 | 5 to 15 | 5 to 15 | 5 to 15
Discussions | 5 to 10 | 10 to 20 | 0 | 1 to 10 | 0
Negotiations | 5 to 10 | 5 to 10 | 1 to 10 | 1 to 10 | 5 to 10
Responsibility Review | 1 to 5 | 1 to 5 | 1 to 5 | 1 to 5 | 0
Award Decision Document | 1 to 2 | 1 to 2 | 1 to 2 | 1 to 2 | 1 to 2
Contract Review (Legal, etc) | 10 to 15 | 15 to 20 | 10 to 15 | 10 to 15 | 10 to 15
Award | Stop | Stop | Stop | Stop | Stop
Estimated Number of Calendar Days | 88 to 177 | 138 to 242 | 59 to 167 | 60 to 177 | 37 to 82
Other Potential Schedule Impacts
CFO Review (2) | 40-60 | 40-60 | 40-60 | 40-60 | 40-60
Acquisition Strategy Review Board (ASRB) | 10 to 20 | 10 to 20 | 10 to 20 | 10 to 20 | 10 to 20
Public Affairs Notification >$3.5M | 2 | 2 | 2 | 2 | 2(3)
EEO Pre-Award Clearance (Other than Construction) >$10M | 30 | 30 | 30 | 30 | 30(4)
Number of Calendar Days with Potential Schedule Impacts | 170-289 | 220-354 | 141-279 | 142-289 | 119-194
(1) Includes a single sources to socially and economically disadvantaged businesses (SEDB)/8(a) and
service-disabled veteran owned small businesses (SDVOSB)
(2) All acquisitions (e.g., contracts, interagency agreements, other transactions, etc.) over $10 million require CFO approval. This includes
modifications that increase the contract ceiling price over $10 million or the authorized CFO ceiling limit as defined in AMS Procurement
Guidance section T3.2.1.4.
(3) Required only for mods over $10M when the base was not originally coordinated
(4) Required if a mod increases the total contract value to $10M or more
Action | Administrative Mods | Simplified Purchase | Delivery/ Task Orders (Incl FSS) | Exercise Option
Complete PR Package Received | Start | Start | Start | Start
OSBD Acceptance | 0 | 1 to 5 | 1 to 5 | 0
Market Analysis | 5 to 10 | 5 to 10 | 5 to 10 | 5 to 10
Announcement/Synopsis | 0 | 0 | 0 | 0
CO Review Requirements/Draft SIR | 5 to 10 | 5 to 10 | 5 to 10 | 0
SIR Review (Mgmt, Legal, etc) | 0 | 10 to 15 | 10 to 15 | 10 to 15
SIR | 0 | 5 to 30 | 5 to 30 | 0
Proposal/Quote/Technical Evaluation | 0 | 1 to 5 | 1 to 15 | 0
Discussions | 0 | 1 to 2 | 1 to 10 | 0
Negotiations | 0 | 1 to 3 | 1 to 10 | 5 to 10
Responsibility Review | 0 | 1 to 2 | 1 to 2 | 0
Contract Review (Legal, etc) | 5 to 10 | 5 to 10 | 5 to 10 | 5 to 10
Notification to contractor- Exercise of option | 0 | 0 | 0 | 30
Award Decision Document | 0 | 1 to 2 | 1 to 2 | 1 to 2
Award | Stop | Stop | Stop | Stop
Estimated Number of Calendar Days | 15 to 30 | 36 to 94 | 36 to 119 | 56 to 77